## Version
Project | TMH - Accounting Hub
Description | This document provides details of dependencies, Assumptions & Risks for IT Resilience
Document History
Version | Date | Author | Comments
Draft v0.1 | 2014-08-18 | Krishna Dattatreya | Initial draft version.

## MLPD
MLPD Tasks
| Main | Sections | Sub-Sections | Scheduled Completion
1 | Background |  |  | Aug 18th - Aug 19th
2 | Scope | In-Scope/Out of scope |  | Aug 18th - Aug 19th
3 | Assumptions |  |  | Aug 18th - Aug 19th
4 | Dependencies |  |  | Aug 18th - Aug 19th
5 | Risks |  |  | Aug 18th - Aug 19th
6 | Service Functionality |  |  | Aug 20th
Account Enquiry
Account Posting
7 | Use Case Model |  |  | Aug 21th - Aug 22nd
Account Enquiry
Account Posting
8 | Platform Design |  |  | Aug 25th - Aug 29th
Account Enquiry to HBOS Platforms
Implementation Model
Sequence Diagram
Activity Diagram
Account Posting to HBOS Platforms
Implementation Model
Sequence Diagram
Activity Diagram
|  | Process unprocessed messages held in failed nodes |  | Sept 1st
|  | TODS Interfaces |  | Sept 2nd
|  | Exception Scenarios |  | Sept 2nd
9 | Non Functional Requirements |  |  | Sept 3rd
| Review & Comments implementation |  |  | Sept 3 - Sept 5
Assumptions: Batch/File Processing is not being done by Accounting Hub.
Based on Current AD. No Further changes on AD
Interface specs are ready for H-HBOS systems

## Dependencies
Dependencies
1 | Interface specs from wCBS | Interaction, Message format(xsd/wsdl), APIs if any,any gateways,timeouts
2 | Interface specs from NCA
3 | Interface specs from TD01
4 | Interface specs from IF-TD01
5 | Interface specs from IF-Lynx
6 | Interface specs from TODS
7 | Interface specs from AMD | Contras,Aggrigation,Collection Accounts, HOCA Accounts,Sequence,Platform Availability,payment mode, payment type,
8 | Interface specs from rCBS ( If any new API to handle Contra/settlement Postings)
1 | Mappings - Request & Response
2 | ACH to NCA(Request), NCA to ACH(Response)
3 | ACH to wCBS, wCBS to ACH
4 | ACH IF-Midtier - IF-TD01, IF-TD01 to ACH
5 | ACH to IF-Midtier-Lynx, Lynx to ACH
6 | ACH to TD01, TD01 to ACH
7 | ACH to TODS
Error Codes for each of HBOS Platforms & correstponding ACH error codes from EAD/BA
File/Batch processing component

## Assumptions
Assumptions
1 | AMD will send the posting type(Single/Aggregated) to accouting hub
2 | AMD will send the posting mode (File/Online) to accouting hub
3 | Creation of aggregated entries from individual posting transactions will be implemented in AMD and it will be shared with Accouting hub
4 | AMD will send product platform availability to accouting hub
5 | Accounting hub will not have any implicit postings. it will generate the posting entries based on the account model configured within AMD:GetNPA
6 | AMD will send sequence of entries to be passed to a product platform
7 | Compensation entries will be sent by AMD if service involves multiple steps and for failure as well. If there are no compensating entries Accounting hub will not be able to complete the rollback of the posting transaction.
8 | AMD will provide settlement contra for posting to rCBS platform.
9 | AMD to provide Collection account details and HOCA Account details to Accouting Hub. Account Master data will load the HOCA accounts file for Corporate and Commercial customers.
10 | In case of File/Batch processing, Accouting Hub will just pass the entries to a shared database(TBD)

## Risks
Risks
1 | Since AMD is providing the product platform identity, the accouting Hub existing code to be modified. Need to do regression testing of services of accouting hub including the ones moved to production.
2 | Performance: Accounting hub will have to orchestrate multiple calls over HTTP and MQ to fetch customer details from AMD and route it to various product platforms There is a potential risk on the response time which has to be mitigated based on NFT test results
3 | The current service is for online postings only. It cannot generate a posting file. For file posting, Accoutning Hub will be storing the data in the database. The potential risk exist if the File/Batch posting component fails to identify the Accouting Hub format.