## LLD Components
| Component/Task | Flow | FlowName | Duration (Days) | Complexity | % Completion | Start Date | End Date | Dependencies | Assigned To | Functions, Remarks
1 | External Servers | 1. InterfaceHandler - AIS |  | 5 |  | 10% | 2011-11-03 | 2014-11-07
|  | 2. InterfaceHandler - APS |  | 5 |  | 10% | 2011-11-03 | 2014-11-07
2 | HUB Adapters | 1. WMQ Handlers |  | 5 |  | 20% | 2014-10-20 | 2014-10-27 |  |  | setup CCID -
|  |  | ACH_COMMON_WMQ_RECEIVER_SF | [7 empty] | Adding MQRFH2 Header message - UDP
ACH_COMMON_WMQ_SENDER_SF
|  | 2. HTTP Handler |  | 5 |  | 20% | 2014-10-20 | 2014-10-27
|  |  | ACH_COMMON_WMQ_GATEWAY_MsgFlows | [7 empty] | A Flag should be provided to identify MQ Header To Save the MQ header and send back the header in the response
ACH_COMMON_WMQ_GATEWAY_MsgFlows
3 | MicroKernel | 1. FlowControler |  | 10 | High | 10% | 2014-10-20 | 2014-11-04
|  | 2. mapRouter |  | 10 |  | 10% | 2014-10-20 | 2014-11-04
|  | 3. Validation |  | 5 |  | 20% | 2014-10-27 | 2014-10-31 | POC |  | POC on regex ; RegEx not supported by ESQL
|  | 4. AuditHandler |  | 5 |  |  | 2014-10-27 | 2014-10-31 | POC |  | Bulk Auditing ---- ??
|  | 5. ExceptionHandler |  | 5 |  | 20% | 2014-10-20 | 2014-10-27 | POC |  | Syslog updating ? Is it feasible?
4 | InternalServers
|  | 1. GroupControler & TCM |  | 10 | High | 10% | 2014-11-03 | 2014-11-14
|  | 2. Persistence |  | 5 |  | 10% | 2014-10-20 | 2014-10-27
|  | 3. TimeOutHandler |  | 5 |  |  |  |  | POC
|  | 4. Aggregation |  | 3 |  | 10%
|  | 6. BatchControler |  | 10 | High | 10% | 2014-10-20 | 2014-11-04
a. BatchEntryPost
b. SendBatchControl
c. SendBatchStatus
|  | 7. Stand-In |  | 5 |  |  | 2014-11-03 | 2014-11-07
|  | 8. RecoveryMesageHandler |  | 10 | High | 10% | 2014-11-03 | 2014-11-14
a. Configure level b. Flow level
|  | CanonicalModeling | Control header | 3 |  | 10% | 2011-11-10 | 2014-11-12
|  | Throttling |  | 3 |  | 10% | 2011-11-10 | 2014-11-12
5 | MQ Design |  |  | 5 |  | 0% | 2014-11-03 | 2014-11-07
6 | DB Design |  |  | 5 |  | 10% | 2014-11-03 | 2014-11-07
7 | Policy Settings |  |  | 5 |  | 10% | 2014-10-27 | 2014-10-31
8 | Review of Specs |  |  | 5
9 | Delivery of LLD for SME review |  |  | 5
10 | Incorporating SME review comments |  |  | 5

## Build Phase
Build Phase
maps | 1. AMD -getNPADetails | Reuse & Enhance
| 2. NCA | New
| 3. TD01 | New
| 4. wCBS | New
| 5. IF-Lynx | New
| 6. IF-TD01 | New

## POCs
1 | Message Transformation | Identify modifying the existing code base for the transformation of
http, soap messages - xml to soap & MQ to soap, MQ to http for handler
2 | Dynamic map routing | The maps to be called dynamically. List out all the options available Pros/Cons of each option and to come out with the suggested option based on the POC outcome. | Option1 | route to lable | Option 2 | Queue | Option 3 | pub/sub | Option 4 | esql procedure
3 | Timout Handler | list out the options
4 | Global Cache | Using of Global Cache for sharing of variables between flows in different Egs |  | option to Extreme scale
5 | Validation Enhancement | Using Regular Expression or other dynamic method for validation
6 | Bulk Auditing | To audit the transactions in bulk.
7 | Leader election for nodes failure
| Timeout Handler | 1. Single Schema -
| Bulk Auditing | Get 50 msgs. With one single insert multiple inserts.
Control Queue - Controle Flow will put a message queue

## Design
Flow Controller - Enquiry
Seq Steps | Steps |  |  | mapRouter |  | maps
1 | receiverRequest |  |  | receiveRequest |  | ReqIFW
2 | call Validation |  |  | mapName |  | RespIFW
3 | generateUniqueSeqNo |  |  | InvokeMap |  | ReqAMD
| Auditing | Persistence service |  | SendResponse |  | ReqrCBS
4 | IdentifyProductPlatform | ---->mapRouter ---->reqAMDmap |  |  |  | reqCMN
| Auditing |  |  |  |  | reqwCBS
5 | accountEnquiry | ---->mapRouter ---->reqPPmap |  |  |  | reqNCA
| Auditing |  |  |  |  | reqIFMidtier
6 | getaccountIndicators | ---->mapRouter ---->reqPPmap
Auditing
7 | buildResponse | ---->mapRouter ---->respIFWmap
Client | Sequence
TBT-SOC | 1-2-3-4-5-6-7
PE | 1-2-3-4-7
GPP | 1-2-3-4-5-6-7
Flow Controller - Posting
[5 empty] | SeqSteps | Steps
| Internal Servers |  |  |  | 1 | receiverRequest
|  | AMD |  |  | 2 | valiation |  |  |  |  | State Table | Policy
|  | Model - Req/Resp |  |  | 3 | generateUnqueSeqNo |  |  |  |  | TransactionNo | Service ID | 1
|  | CurrentState |  |  | 4 | Auditing |  |  |  |  | currentState | ServiceName | AIS
|  | NextState |  |  | 5 | getAccountInformation | ---->mapRouter ---->reqAMDmap |  |  |  | nextState | ClientID
[6 empty] | Auditing | [5 empty] | ResponseTime
| MQMD |  |  |  | 6 | getNPADetails | ---->mapRouter ---->reqAMD-NPAmap
| MQRFH2/usr |  |  |  |  | Auditing
| Control Header |  |  |  | 7 | platformPosting | ---->mapRouter ---->reqPlatformmap
| State Management Header |  |  |  | 8 | buildResponse | ---->mapRouter ---->respIFWmap
Body
State Table
|  |  | currentState | nextState | Model | TargetSystem | Flow Name | Destination | Transformation Required? | Mode
| Policy |  | receiveIFWRequest | Validatation | Sync | ACH | Validaton | Q1 | N | Seq
| MessageType |  | Validation | getAccountInformation | Sync - Req/Resp | AMD | getAccountInfo | Q2 | Y | Seq
| SourceSystem |  | getAccountInformation | getNPADetails | Sync - Req/Resp | AMD | getNPADetaisl | Q3 | Y | Seq
Service
| Interface Handler | SOC Enquiry
AIS
APS
IPS
| Policy |  | message type | Source System | Service
AIS | External Policy | SOC Enquiry, GPP Enquiry | Request | SOC | AIS | Soc Enquiry | IdentifyPP
| Internal Policy | Flow Controler, State table… |  |  |  |  | getAccountInformation
rCBSEnquiry
EnquiryOfIndicators
CMNSysEnquiry
Model-ID
GPP Enquiry
InterfaceHandler
receiveIFWRequest
sendIFWResponse
IdentifyProductPlatform
rcbsE540ReqHandler
rcbsE540RespHandler
rcbsE184ReqHandler
rcbsE184RespHandler
rcbsE434ReqHandler
rcbsE434RespHandler
commonReqHandler
commonRespHandler
| Sync Req/Resp | getAccountInformation | Both operations are Isolated. Each operation will have an independent Flow
getNPADetails
| Async Req | IFWRequestHandler | Receive Request from TMH, Transform, Send to AIS Request Queue
|  | GPPRequestHandler | Receive Request from GPP, Transform, Send to AIS Request Queue
|  | rCBSRequestHandler | Receive Request From Controler, Transform, Send to rCBS Request Queue
|  | CMNRequestHandler | Receive Request From Controler, Transform, Send to CMN Request Queue
|  | HBOS-wCBSRequestHandler | Receive Request From Controler, Transform, Send to wCBS Request Queue | for Online Posting | Customer & NPA
|  | HBOS-NCARequestHandler | Receive Request From Controler, Transform, Send to NCA Request Queue | for Online Posting | Customer & NPA
|  | HBOS-TD01RequestHandler | Receive Request From Controler, Transform, Send to TD01 Request Queue | for Online Posting | Customer & NPA
|  | HBOS-IF-MidTierRequestHandler | Receive Request From Controler, Transform, Send to IF-MidTier Request Queue | for Online Posting | Customer & NPA
|  |  |  | TransID | CustomerPlatform | CustomerPosting | NPA Platform | NPA Posting | Compensation | Posting Status
| Async Resp | PlatformPostingHandler |  | 12345 | wCBS | 123 | rCBS | 456 | 5555 | Success
|  | NPAPostingHandler |  |  |  |  | NCA | 789 | 6666 | Suceess
|  |  |  | 54321 | NCA | 321 | rCBS | 654 | 1111 | Suceess
[7 empty] | wCBS | 987 | 2222 | Failed
[7 empty] | TD01 | 789 | 3333 | Suceess
[7 empty] | IF-Midtier | 678 | 4444 | Failed