## Details
Service | ProjectName | Schema Name | Flow Name | Type | Update/ Reuse | Existing Functionality | Required Changes | Status | Remarks
Common | ACH_COMMON_AUDIT_MsgFlows | com.lbg.ach.common.audit | ACH_COMMON_AUDIT_MF | MF | Update | 1. Extract Audit Request message from Queue 2. Log the message in the TAL_AUDIT_LOG table | 1. Check on changing the name of the flow. Avoid usage of Common term | Completed | 1. Project and flow names are changed
Common | ACH_COMMON_AUDIT_MsgFlows | com.lbg.ach.common.audit | ACH_COMMON_AUDIT_SF | SF | Update | 1. Prepare audit message based on the audit details provided in the main flow 2. Send the Audit message to Audit mainflow queue based on the cached from (TAC_AUDIT_CONFIG) table 3. Send the Audit message to Auditing component if auditing is enabled for the Audit point | 1. Get the audit description from the table. 2. Check on changing the name of the flow. Avoid usage of Common term | InProgress | 2. Project and flow names are changed
Common | AH_COM_AUDIT-msg_flows | com.lbg.ach.common.audit | ACH_COM_AUD_PRC | MF | Delete | NA | NA | Open
Common | AH_COM_AUDIT-msg_flows | com.lbg.ach.common.audit | ACH_COM_AUD_RCV_SF | SF | Delete | NA | NA | Open
Common | ACH_COMMON_EXCEPTION_HANDLER_MsgFlows | com.lbg.ach.common.exception | ACH_COMMON_EXCEPTION_HANDLER_MF | MF | Update | 1. Extracts error information from MQRFH2 header 2. Insert the error details into TEL_EXCEPTUION_LOG table | 1. Check on changing the name of the flow. Avoid usage of Common term | Completed | 1. Project and flow names are changed
Common | ACH_COMMON_EXCEPTION_HANDLER_MsgFlows | com.lbg.ach.common.exception | ACH_COMMON_EXCEPTION_HANDLER_SF | SF | Update | 1. Extracts error information from input exception list and environment tree 2. Inserts the error details in the MQRFH2 Header | 1. Check on changing the name of the flow. Avoid usage of Common term | Completed | 1. Project and flow names are changed
Common | AH_COM_EXCEPTION_HANDLING-msg_flows | com.lbg.ach.common.exception | ACH_COM_EXC_PRC | MF | Delete | NA | NA
Common | AH_COM_EXCEPTION_HANDLING-msg_flows | com.lbg.ach.common.exception | ACH_COM_EXC_RCV_SF | SF | Delete | NA | NA
Common | ACH_COMMON_WMQ_GATEWAY_MsgFlows | com.lbg.ach.common.wmq.gateway | ACH_COMMON_WMQ_RECEIVER_SF | SF | Update | 1. This flow performs first point processing immediately after receiving the message from a system. | 1. Include Exception handling and Auditing Sub flows 2. Check on changing the name of the flow. Avoid usage of Common term | Completed | 1. Included the Exception and Audit subflows 2. Project and flow names are changed
Common | ACH_COMMON_WMQ_GATEWAY_MsgFlows | com.lbg.ach.common.wmq.gateway | ACH_COMMON_WMQ_SENDER_SF | SF | Update | 1. This flow performs preprocessing required before sending msg to the accounting system | 1. Include Auditing Subfllow 2. Check on changing the name of the flow. Avoid usage of Common term | Completed | 1. Included Audit subflow 2. Project and flow names are changed
Common | AH_MQ_GATEWAY | com.lbg.ach.common.mqgateway | ACH_COM_MQ_RCV_SF | SF | Delete | NA | NA | Open
Common | AH_MQ_GATEWAY | com.lbg.ach.common.mqgateway | ACH_COM_MQ_SNDR_SF | SF | Delete | NA | NA | Open
Common | ACH_COMMON_UTILITY_FunctionsAndProcedures | com.lbg.ach.common.utilities | ACH_COMMON_UTILITY_Functions | ESQL | Update | 1. This ESQL is using for creating unique sequence number in Acc Hub. | 1. Identify any reusable functions/procedures and add in this project | Open
Common | TBD | TBD | TBD | SF | New | NA | 1. Create HTTP Request component | Open
Common | ACH_COM_VALIDATION-msg_flows | com.lbg.ach.common.validation | ACH_COM_VAL_PRC_SF | SF | Delete | NA | NA
Common | ACH_COMMON_VALIDATION_MsgFlows | com.lbg.ach.common.validation | ACH_COMMON_VALIDATION_SF | SF | Update | 1. This flow will do validation of message against a set validation rules. | 1. Add new validation rule when the fields are repeating | InProgress
Common | ACH_COMMON-msg_flows | com.lbg.ach.common | ACH_Common | SF | Reuse | NA | NA | Open
AIS | ACH_AIS_BNS_MsgFlows | com.lbg.ach.ais.bns | ACH_AIS_BNS_REQ_MF | MF | Reuse | 1.This flow will create message in F845 format. 2.Route the message to BNS system 3.Send one copy of message to expiry queue | No changes required | NA
AIS | ACH_AIS_BNS_MsgFlows | com.lbg.ach. | ACH_AIS_BNS_RES_MF | MF | Reuse | 1. This flow will receive response from BNS system 2. Updates database. | No changes required | NA
AIS | ACH_AIS_F845_BNS_V01_MsgSet | NA | NA | MS | Reuse | This Message set is used to validate BNS Request and Response | No changes required | NA
AIS | ACH_AIS_COMMON_MsgFlows | com.lbg.ach.ais.common | ACH_AIS_COMMON_REQ_MF | MF | Reuse | 1.This flow will create message in common format. 2.Route the message to common system 3.Send one copy of message to expiry queue | No changes required | NA
AIS | ACH_AIS_COMMON_MsgFlows | com.lbg.ach.ais.common | ACH_AIS_COMMON_RES_MF | MF | Reuse | 1. This flow will receive response from common system 2. Updates database | No changes required | NA
AIS | ACH_AIS_COMMON_V01_MsgSet | NA | NA | MS | Reuse | This Message set is used to validate Common Request and Response | No changes required | NA
AIS | ACH_AIS_RCBS_MsgFlows | com.lbg.ach.ais.rcbs | ACH_AIS_RCBS_REQ_MF | MF | Reuse | 1.This flow will create message in E540 and E184 format. 2.Route the message to rcbs system 3.Send one copy of message to expiry queue | No changes required | NA
AIS | ACH_AIS_RCBS_MsgFlows | com.lbg.ach.ais.rcbs | ACH_AIS_RCBS_RES | MF | Update | 1. This flow will receive response from rcbs system 2. Updates database 3. If the rcbs response is fail, then will call compensation sub flow for processing. | 1. Add _MF at the end of the ESQL file and Flow name | Open
AIS | ACH_AIS_RCBS_MsgFlows | com.lbg.ach.ais.rcbs | ACH_AIS_RCBS_COMPENSATION_SF | SF | Reuse | 1. The module will invoked only when the rcbs E540 request is fail 2. It will remove the first accountnumber and sortcode from the E540 request 3. will resend the request again | No changes required | NA
AIS | ACH_AIS_RCBS_MsgFlows | com.lbg.ach.ais.rcbs | CommonMappingFile | ESQL | Reuse | This is using for rCBS E184 and E540 request mapping. | 1. Need to cross check if the functions/procedure defined can be made generic or remove them | Open
AIS | ACH_AIS_E184_RCBS_MsgSet | NA | NA | MS | Reuse | This Message set is used to validate E184 rCBS Structure. | No changes required | NA
AIS | ACH_AIS_E540_RCBS_v03_MsgSet | NA | NA | MS | Update | This Message set is used to validate E540 rCBS Structure. | 1. Update the name to make version number from v03 to V03 | Open
AIS | ACH_AIS_CORE_MsgFlows | com.lbg.ach.ais.core | ACH_AIS_CORE_REQ_MF | MF | Update | 1. This flow Receive request from TMH/GPP 2. Will perform bussiness validations . | 1. Update the flow to get all the orchestration details from table | Open
AIS | ACH_AIS_CORE_MsgFlows | com.lbg.ach.ais.core | ACH_AIS_CORE_RES_MF | MF | Update | 1. This flow will create IFW response message 2. It will send to TMH/GPP. | 1. Update the flow to get details from table and execute | Open
AIS | ACH_AIS_CONTROLLER_RES_MF_MsgFlows | com.lbg.ach.ais.controller.core | ACH_AIS_CONTROLLER_REQ_SF | SF | Update | 1. This flow will split the AMD message 2. Routes it to rCBS/COMMON/BNS handler flows based on product platform name. |  | Open
AIS | ACH_AIS_CONTROLLER_RES_MF_MsgFlows | com.lbg.ach.ais.controller.core | ACH_AIS_CONTROLLER_RES_MF | MF | Update | 1. This flow will check whether all group has completed 2. Then it will send a trigger message to core resposne handler flow. |  | Open
AIS | ACH_AIS_GROUP_CONTROLLER_MsgFlows | com.lbg.ach.ais.controller.util | ACH_AIS_GROUP_CONTROLLER | MF | Update | 1. This flow will do the DB operations in TGC_GROUP_CONTROL and TGD_GROUP_DETAIL tables. |  | Open
AIS | ACH_AIS_MQBROWSING-msg_flows | com.lbg.ach.ais.expiry | ACH_AIS_MQBROWSING | MF | Update | 1. This flow will browse the message from expiry queue | 1. Update the name of the project 2. Update name of the message flow | Open
AIS | ACH_AIS_IFW_V01_MsgSet | NA | NA | MS | Reuse | NA | No changes required | Open
AIS | ACH_AIS_IFW_V03_MsgSet | NA | NA | MS | Reuse | This Message set is used to validate IFW Structure. | No changes required | Open
AIS | ACH_AIS_AMD_getGrpAcct_V01_MsgSet | NA | NA | MS | Delete | NA | 1. Delete the project after ensuring its no more required | Open
AIS | ACH_AIS_AMD_getGrpAcct_V02_MsgSet | NA | NA | MS | Delete | NA | 1. Delete the project after ensuring its no more required | Open
AIS | ACH_AIS_AMD_getGrpAcct_V03_MsgSet | NA | NA | MS | Delete | NA | 1. Delete the project after ensuring its no more required | Open
AIS | ACH_AIS_AMD_getGrpAcct_V04_MsgSet | NA | NA | MS | Update | This Message set is used to validate AMD getGroupAcct Structure. |  | Open
AIS | ACH_AIS_OCIS_F929_V01_MsgSet | NA | NA | MS | Delete | NA | 1. Delete the project after ensuring its no more required | Open
AIS | ACH_AIS_OCIS_F929_V02_MsgSet | NA | NA | MS | Update | This Message set is used to validate F929 OCIS Structure. |  | Open
AIS | ACH_AIS_PLATFORM_IDENTIFY_GRP_MsgFlows | com.lbg.ach.ais.identifyandgrp.core | ACH_AIS_AMD_ACC_GROUPING_MF | MF | Update | This flow will create AMD request message and will invoke the web service. |  | Open
AIS | ACH_AIS_PLATFORM_IDENTIFY_GRP_MsgFlows | com.lbg.ach.ais.identifyandgrp.core | ACH_AIS_IDENT_ACC_PLATFORM_MF | MF | Update | 1. This flow will create OCIS request message(F929 format) and will invoke the web service. |  | Open
AIS-EPay | ACH_AIS_GPP_CORE_HANDLER_MsgFlows | com.lbg.ach.ais.gpp.core | ACH_GPP_CORE_HANDLER_REQ_MF | MF | Reuse | 1. This flow will receive message from GPP system. 2.Convert to GPP to IFW format 3.Validate the ifw request message against the schema. |  | Open
AIS-EPay | ACH_AIS_GPP_CORE_HANDLER_MsgFlows | com.lbg.ach.ais.gpp.core | ACH_GPP_CORE_HANDLER_RES_MF | MF | Reuse | 1.This flow will create the GPP response message. 2.Validate the response message against schema. |  | Open
AIS-EPay | ACH_AIS_GPP_MQBROWSING-msg_flows | com.lbg.ach.ais.gpp.expiry | ACH_AIS_GPP_MQBROWSING | MF | Reuse | This flow will browse the message from expiry queue |  | Open
AIS-EPay | ACH_AIS_GPP_REQ_v01_Msgset | NA | NA | MS | Delete | This Message set is used to Validate GPP Request. | 1. Delete the project after ensuring its no more required | Open
AIS-EPay | ACH_AIS_GPP_REQ_V01_MsgSet | NA | NA | MS | Reuse | This Message set is used to Validate GPP Response. |  | Open
APS | ACH_APS_COMMON_UTILITY_FunctionsAndProcedures | com.lbg.ach.aps.common.utilities | ACH_APS_COMMON_UTILITY_Functions | ESQL | Update | This procedure is using for define namespaces. |  | Open
APS | APS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.aps.core | ACH_APS_ACC_POST_CORE_HANDLER_REQ | MF | Update | 1.Receive the IFW Message from TMH. 2.Validate the IFW Message. 3.Creaete an Internal message to invoke GetFullAccountInformation flow . 4.If the payment is rejected or Timed out ,Then it send back the responce to TMH. 5.If the web service call is success the it will send to ACH_APS_CORE_RCBS_REQ flow. |  | Open
APS | APS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.aps.core | ACH_APS_ACC_POST_CORE_HANDLER_RES | SF | Update | 1.Creating TMH envelope. 2.Validate the ifw response message. 3.Send response to TMH. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.common | SMH_Create | ESQL | Delete | NA |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.mappings.rcbs | MAP_RCBS_E434_REQ_SF | SF | Update | 1.Create E434 Request Message. 2.Validate the Request Message. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.mappings.rcbs | MAP_RCBS_E434_RES_SF | SF | Update | 1.Create E434 Response Message. 2.Validate the Response Message. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.mappings.rcbs | MAP_RCBS_E509_REQ_SF | SF | Update | 1.Create E509 Request Message. 2.Validate the Request Message. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.mappings.rcbs | MAP_RCBS_E509_RES_SF | SF | Update | 1.Create E509Response Message. 2.Validate the Response Message.. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.rcbs | ACH_APS_CORE_RCBS_REQ | MF | Update | 1. This flow will call the subflows for E434/E509 request mapping. 2.If standin is required, then will do standin the payment else send it to rCBS 3.Send a copy of message to expiry queue. |  | Open
APS | APS_ACC_POST_RCBS_HANDLER_MsgFlows | com.lbg.ach.aps.rcbs | ACH_APS_CORE_RCBS_RES | MF | Update | 1.Receive Message from RCBS product platform. 2.Validate the rCBS response Message . 3.Call E434 response mapping sub flow |  | Open
APS | APS_E434_RCBS_MsgSet | NA | NA | MS | Reuse | This message set is used to validate E434 API message format. |  | Open
APS | APS_E509_RCBS_MsgSet | NA | NA | MS | Reuse | This message set is used to validate E509 API message format. |  | Open
APS | ACH_APS_STANDIN_MONITOR_MsgFlows | com.lbg.ach.aps.standinmonitor | ACH_APS_STANDIN_MONITOR | MF | Update | 1.This Flow is used to reject payments for which are not processed within the stipulated time. 2.Update the TSL_STANDIN_LOG table for the rejected payments. |  | Open
APS | APS_STAND_IN_MsgFlows | com.lbg.ach.aps.standin | ACH_APS_SEND_QUALIFIED_RESPONSE_SF | SF | Update | This flow is used to create a ifw response body. |  | Open
APS | APS_STAND_IN_MsgFlows | com.lbg.ach.aps.standin | ACH_APS_STAND_IN_CONTROLLER | MF | Update | 1.This flow will receive trigger message from AMD. 2.Retrieve the payment details which is 'In Process' from TSL_STANDIN_LOG table. 3.Send to rCBS platform for posting. |  | Open
APS | APS_STAND_IN_MsgFlows | com.lbg.ach.aps.standin | ACH_APS_STAND_IN_REPORT | MF | Update | This flow is used to Browse the Expired Message |  | Open
APS | APS_STAND_IN_MsgFlows | com.lbg.ach.aps.standin | ACH_APS_STANDIN_PROCESS_SF | SF | Update | This flow is used to store the payment in TSL_STANDIN_LOG table if standin is required . |  | Open
APS | APS_StandIn_MsgSet | NA | NA | MS | Update | This message set is used to validate trigger message from AMD. |  | Open
APS | ACH_AMD_getNPADetails_v01_MsgSet | NA | NA | MS | Delete | This Message Set is used to validate getNPADetails RequestMessage. |  | Open
APS | ACH_AMD_getNPADetails_v03_MsgSet | NA | NA | MS | Reuse | This Message Set is used to validate AMD Request |  | Open
APS | ACH_AMD_V03_MsgSet | NA | NA | MS | Delete | This Message Set is used to validate CODS_F929 API Request. |  | Open
APS | ACH_AMD_V04_MsgSet | NA | NA | MS | Delete | NA | NA | Open
APS | ACH_AMD_V05_MsgSet | NA | NA | MS | Reuse | NA | NA | Open
APS | ACH_CODS_F929_V02_MsgSet | NA | NA | MS | Delete | NA | NA | Open
APS | ACH_CODS_F929_V03_MsgSet | NA | NA | MS | Reuse | NA | NA | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.amd | ACH_GET_FULL_ACC_AMD_NPA_SF | SF | Update | 1.This flow will create a NPA request. 2.Validate the request message. 3.Send the request message to NPA system . |  | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.amd | ACH_GET_FULL_ACCT_AMD_MAP_SF | SF | Update | This Message flow is used to create a AMD Request Message. |  | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.amd | ACH_GET_FULL_ACCT_AMD_SENDER_SF | SF | Update | This Message flow is used to validate and send the AMD Request Message . |  | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.cods | ACH_GET_FULL_ACCT_CODS_MAP_SF | SF | Update | This Message flow is used to create a OCIS Request Message. |  | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.cods | ACH_GET_FULL_ACCT_CODS_SENDER_SF | SF | Update | This Message flow is used to validate and send the OCIS Request Message and get response OCIS. |  | Open
APS | APS_GetFullAccountInformation_MsgFlows | com.lbg.ach.aps.getfullaccinfo.core | ACH_GET_FULL_ACCT_INFO | MF | Update | This flow will initiate OCIS,AMD and NPA web service call. |  | Open
APS | ACH_APS_IFW_v01_MsgSet | NA | NA | MS | Reuse | This Message Set is used to validate APS_IFW Structure. |  | Open
APS | ACH_LCS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.lcs.core | ACH_LCS_CORE_HANDLER_REQ | MF | Update | 1.Receive Request Message from LCS System. 2.Call the sub flow for mapping to ifw format |  | Open
APS | ACH_LCS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.lcs.core | ACH_LCS_CORE_HANDLER_RES | MF | Update | 1.Call the subflow for Mapping to LCS format. 2. Send the response message to LCS system. |  | Open
APS | ACH_LCS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.lcs.mappings | MAP_APS_TO_LCS_SF | SF | Update | 1. This flow will create LCS response message 2.Validate the LCS response message. |  | Open
APS | ACH_LCS_ACC_POST_CORE_HANDLER_MsgFlows | com.lbg.ach.lcs.mappings | MAP_LCS_TO_APS_SF | SF | Update | 1.Convert LCS Format Message to IFW Format Message. 2.Validate the ifw request message. |  | Open
APS | LCS_MsgSet | NA | NA | MS | Delete | This message set is used to validate LCS format request message. |  | Open
APS | LCS_Request_MsgSet | NA | NA | MS | Update | This message set is used to validate LCS format response message. |  | Open
APS | LCS_Response_MsgSet | NA | NA | MS | Update | This message set is used to validate LCS format response message. |  | Open
AIS | NA | com.lbg.ach.ais.tbtsoc.amd | NA |  | Delete |  | Delete the folder | Open
IPS | ACH_IPS_MQBROWSING-msg_flows | com.lbg.ach.ips.expiry. | ACH_IPS_MQBROWSING | MF | Reuse | This flow will browse the message from expiry queue |  | Open
IPS | ACH_IPS_CORE_HANDLER_REQ-msg_flows | com.lbg.ach.ips.requesthandler | ACH_IPS_CORE_HANDLER_REQ | MF | Reuse | 1.This flow will recieves ifw request message. 2.Validates the message |  | Open
IPS | ACH_IPS_CORE_HANDLER_RES-msg_flows | com.lbg.ach.ips.responsehandler | ACH_IPS_CORE_HANDLER_RES | MF | Reuse | 1.This flow will create ifw response message 2.Validate the ifw response 3.Send the response back to TMH. |  | Open
IPS | ACH_IPS_CODS_msg_flows | com.lbg.ach.ips.cods | ACH_IPS_CALL_CODS_SF | SF | Reuse | This flow will create & validate CODS request, invoke the OCIS webservice. |  | Open
IPS | ACH_IPS_RCBS_E516_REQ-msg_flows | com.lbg.ach.ips.rcbs | ACH_IPS_RCBS_E516_MAP_REQ_SF | SF | Reuse | 1.Create E516 Request Message. 2.Validate the Request Message. |  | Open
IPS | ACH_IPS_RCBS_E516_RES-msg_flows | com.lbg.ach.ips.rcbs | ACH_IPS_MAP_RCBS_E516RES_SF | SF | Reuse | 1.Create E516 response Message. 2.Validate the response Message. |  | Open
IPS | ACH_IPS_RCBS_E516_Msg_Set | NA | NA | MS | Reuse | This Message set is used to validate E516 rCBS Structure. |  | Open
IPS | ACH_IPS_OCISF929_MsgSet | NA | NA | MS | Reuse | This Message set is used to validate F929 OCIS Structure. |  | Open
IPS | InterestPostingService-msg_Set | NA | NA | MS | Reuse | This Message set is used to validate IFW Message Structure. |  | Open

## DoNotDelete (hidden)
Service | Type | Status | MainTask
Common | MF | Open | Update
AIS-EPay | SF | InProgress | Reuse
AIS | ESQL | Completed | New
APS | MS | NA | Delete
IPS

## OthersPoints
1 | Create specific sequences for external system sequences and generate ACH Id from timestamp
2 | Handling rCBS response error code when received with prefixed zeros
3 | Handling rCBS response when the Account details are not found but Body is sent in the response
4 | Add retry logic in the HTTP Calls
5 | Avoid sending duplicate responses in case of Timeout scenario
6 | Change the error description in the Core AIS response flow in case of Internal exception. Do not always send timeout Error response.
7 | Cross check all the Audit description, avoid spelling and grammer mistakes
8 | Set broker user id for all the timeout messages which are sent to Inflight queue
9 | Format StateManagementHeader section
10 | Try to fill in data for all the columns in Audit log table for all Audit points.
11 | Take the Audit descriptions from the table instead of hard coding in the table
12
13
14
15