## Sheet3
sl.no | POC Name | Description | %Complete | Remarks
1 | Message Transformation | Identify modifying the existing code base for transformation of various types of messages | 100% | None
2 | Dynamic map routing | The maps to be called dynamically. List out all the options available | 70% | Currently doing performance testing of Label and Pub-Sub.
3 | Timeout Handler | Option 1: Control using db status | 0% | Complete Blocker. No breakthrough yet.
4 | Global Cache | Using of Global Cache for sharing of variables between flows in different EG s | 0% | We are trying to get hold of support pack IA91.
5 | Validation Enhancement | Using Regular Expressions or other dynamic method for validation | 10% | Understanding usage of JCN under progress
6 | Bulk Auditing | To audit the transactions in bulk. | 50% | 1 approach complete. Analyzed usage of JCN to call DB. Eventually we are facing the same challenge of calling DB using a configurable SQL query.
7 | Leader election for nodes failure | impletment a dynamic leader in token ring kind of algorithm to carry forward the transactions in case a node/server fails | NA | MQ/WMB HA can be impltement but its infra level configuration hence out of scope of the poc definition