## DetailedTaskPlan
Task Id | Priority | Activity | Owner | Planned Date |  | Actual Date |  | Reviews |  |  |  | % Completion | Status | Dependencies |  | Notes | RTC Task | Progress Comments
|  |  |  | Start | End | Start | End | Peer | Date | Lead | Date |  |  | Dependency | Owner
TaskId-1 | 2 | Create XSD for Batch Interface | Sumeet K | 2014-11-17 | 2014-11-18 | 2014-11-17 |  | Sami A |  | Satish M |  |  | InProgress
TaskId-2 | 1 | Update Exception Main Flow | Priya D | Planned Date Start: 2014-11-14; Actual Date Start: 2014-11-14; Reviews Peer: Sumeet K; Reviews Lead: Satish M |  | InProgress | Configuration from Tivoli team | James, Potter |  |  | 14Nov14 > Sumeet to Update the Excel Sheet and share it with Tivoli Team > Satish to get sample log from TMH team
TaskId-3 | 2 | Development of HouseKeeping flow | Sai P | Reviews Peer: Sumeet K; Reviews Lead: Satish M |  | InProgress | None | NA |  |  | 14Nov14 > Satish to review and update back
TaskId-4 | 3 | Create mapping document for IF
TaskId-5 | 3 | Create IF Message Definition
TaskId-6 | 3 | Create Mapping document for wCBS
TaskId-7 | 2 | Update Audit Subflow LLD
TaskId-8 | 2 | Update Exception Main flow LLD
TaskId-9 | 3 | Create Housekeeping LLD
TaskId-10 | 4 | ACH_AUDIT_HANDLER Mainflow | Sai P | Planned Date Start: 2014-11-25; Actual Date Start: 2014-11-25; Reviews Peer: Priya D |  | InProgress
TaskId-11 | 4 | IF Account Posting Message set | Priya D | Planned Date Start: 2014-11-21; Actual Date Start: 2014-11-21; Reviews Peer: Sumeet; Reviews Lead: Satish M |  | InProgress
TaskId-12 | 4 | AMD Message Set
TaskId-13 | 4 | ACH_AUDIT_HANDLER Subflow
TaskId-14 | 4 | Exception Handler Main flow
TaskId-15 | 4 | Exception Handler Sub flow
TaskId-16 | 4 | AIS IFW Message set
TaskId-17 | 4 | APS IFW Message set

## Dependency-Status
External System | Scheme Type | Component | Version/Revision | Receive Date | ADM Review Date | Final Version? | Owner | RAG Status | Notes - External Stakeholders | Notes - Internal Tracking
AMD - AAI | Not Applicable | AMD-AAIS Schema | 1.4.6 1.4.8 | 05/12/2014 20/01/2015 22/01/2015 12/02/2015 | 09/12/2014 27/01/2015 TBD | Yes | AMD |  | As per confirmation changes will be delivered on 6th March | 10122014-ACH ADM checked the schema and looks fine 20012015-Updated schema is received 22012015-Received updated schema 12022015-Received updated artefact from AMD team 24022015-Latest version is shared in the Baseline2 folder 26022015-Alister confirmed to incorporate the changes and deliver the code to ST3 on 6th March
|  | AMD-AAIS Message Format | 1.9.1 1.9.4 | 05/12/2014 20/01/2015 22/01/2015 12/02/2015 | 09/12/2014 27/01/2015 TBD | Yes | AMD |  | As per confirmation changes will be delivered on 6th March | 10122014-Deshdeep to follow up with AMD and TMH team. This is for only one field "MessageType" 15012015-Deshdeep update over OCS that this field is made as an optional field and default value Inbound will be populated. 20012015-Updated document is received 22012015-Received updated artefact 12022015-Received updated artefact from AMD team 24022015-Latest version is shared in the Baseline2 folder 26022015-Alister confirmed to incorporate the changes and deliver the code to ST3 on 6th March
|  | AMD-AAIS Sample Message | 1.4.6 1.4.8 | 20/01/2015 22/01/2015 12/02/2015 | 27/01/2015 TBD | Yes | AMD |  | ACH ADM to review | 10122014-Satish/Krishna to follow up with AMD team 22012015-Received updated artefact 12022015-Received updated artefact from AMD team
|  | AMD-AAIS Mapping Document | 1.0 | 17/11/2014 23/01/2015 | 24/11/2014 23/01/2015 | Need to revisit | BA(Deshdeep) |  | Deshdeep to check what changes are required in the mapping document. | 10122014-Based on message format above minor update will be done. 23012015-Latest changes are updated in the document 12022015-Received updated artefact from AMD team. Deshdeep to check what changes needed in the mapping document. 26022015-Informed Deshdeep that there is a need to revisit the mapping document based on updated schema and message formats.
AMD - GetNPA | Not Applicable | AMD-NPA Schema | 1.2.5 1.2.6 | 10/12/2014 20/01/2015 22/01/2015 | 2015-01-27 | Yes | AMD |  | As per confirmation changes will be delivered on 6th March | 10122014-ACH ADM team to review 08012015-Decided with Sarit that a new field will be introduced in AMD response to send the Batch timings 20012015-Updated schema is received 22012015-Received updated artefact 24022015-Latest version is shared in the Baseline2 folder 26022015-Alister confirmed to incorporate the changes and deliver the code to ST3 on 6th March
|  | AMD-NPA Message Format | 1.9.1 1.9.4 | 10/12/2014 20/01/2015 22/01/2015 12/02/2015 | 27/01/2015 TBD | Yes | AMD |  | As per confirmation changes will be delivered on 6th March | 10122014-ACH ADM team to review 08012015-Decided with Sarit that a new field will be introduced in AMD response to send the Batch timings 20012015-Updated document is received 22012015-Received updated artefact 12022015-Received updated artefact from AMD team 24022015-Latest version is shared in the Baseline2 folder 26022015-Alister confirmed to incorporate the changes and deliver the code to ST3 on 6th March
|  | AMD-NPA Sample Message | 0.8.1 0.10 | 10/12/2014 22/01/2015 12/02/2015 | 27/01/2015 TBD | Draft | AMD |  | Awaiting confirmation from Alister on delivering these changes on 6th March | 10122014-ACH ADM team to review 08012015-Decided with Sarit that a new field will be introduced in AMD response to send the Batch timings 22012015-Received updated artefact 12022015-Received updated artefact from AMD team
|  | AMD-NPA Mapping Document | TBD | TBD | TBD | Need to revisit | BA(Deshdeep) |  | Deshdeep to check what changes are required in the mapping document | 10122014-Deshdeep to cross check on this along with Satish 12022015-Received updated artefact from AMD team. Deshdeep to check what changes needed in the mapping document. 26022015-Informed Deshdeep that there is a need to revisit the mapping document based on updated schema and message formats.
AMD - StandIn Trigger | Not Applicable | AMD-StandIn Schema | TBD | TBD | TBD | TBD | AMD |  | Confirmation received from Somani, Ankit that there are no changes in the old design. Hence marking this component as Green. | 15012015-Discussed with Ankit and Shrinath the availability/unavailability of hHBOS and rCBS is not same. Ankit/AMD ADM will share an email with the details. 21012015-Ankit confirmed no changes in the existing logic.
|  | AMD-StandIn Message format | TBD | TBD | TBD | TBD | AMD |  |  | 15012015-Discussed with Ankit and Shrinath the availability/unavailability of hHBOS and rCBS is not same. Ankit/AMD ADM will share an email with the details. 21012015-Ankit confirmed no changes in the existing logic.
|  | AMD-StandIn Sample message | TBD | TBD | TBD | TBD | AMD |  |  | 15012015-Discussed with Ankit and Shrinath the availability/unavailability of hHBOS and rCBS is not same. Ankit/AMD ADM will share an email with the details. 21012015-Ankit confirmed no changes in the existing logic.
|  | AMD-StandIn Mapping document | TBD | TBD | TBD | TBD | BA(Deshdeep) |  |  | 15012015-Based on the AMD ADM response BA need to cross check if any mapping document is required or modification required 21012015-Ankit confirmed no changes in the existing logic. Hence this artefact is not required.
IF | CHAPS & International | IF-Interface Spec | 1.1 | 03/12/2014 23/01/2015 | 05/12/2014 31/12/2014 23/01/2015 | Yes | BA(Deshdeep) |  | ACH ADM Development InProgress | 10122014-ACH ADM Progressing on this interface 31122014-Revisited the document and there are some open items pending. Deshdeep to cross check
|  | IF-Mapping Document | 1.1 | 03/12/2014 23/01/2015 | 05/12/2014 31/12/2014 23/01/2015 | Yes | BA(Deshdeep) |  | ACH ADM Development InProgress | 10122014-ACH ADM Progressing on this interface 31122014-Revisited the document and there are some open items pending. Deshdeep to cross check
|  | IF-Schema/Copy Book | NA | NA | NA | NA | Haigh Johnathn |  | RISK without copy book message structured created manually, this could lead to rework at later stages. | 10122014-Structure is been created manually by ACH ADM team
|  | IF-Sample Message/File | NA | 2014-12-01 |  | Yes | Haigh Johnathn |  | Can proceed with a open risk of Rework during testing phases | 10122014-ACH ADM is fine with the Sample files
wCBS | International | wCBS-Interface Spec | 1.1 | 2014-12-02 | 2014-01-20 | Yes | BA(Deshdeep) |  | ACH ADM to proceed with the development Need to know the Physical format of the message, as of now continuing with Flat file (Fixed length) | 10122014-Need to have further discussion with Isabel and Alister along with Deshdeep 21012015-Deshdeep has worked on the review comments and shared the updated document in Baseline2 folder
|  | wCBS-Mapping Document | 1.1 | 2014-12-02 | 2014-01-20 | Yes | BA(Deshdeep) |  | ACH ADM to proceed with the development Need to know the Physical format of the message, as of now continuing with Flat file (Fixed length) | 10122014-ACH ADM to have a look 21012015-Deshdeep has worked on the review comments and shared the updated document in Baseline2 folder
|  | wCBS-Schema/Copy Book | N/A | 2014-12-09 | 2014-12-09 | No | Isabel Taggart |  | Can proceed with a open Risk of rework during testing phase | 09122014-Copy book shared but can not be used as is 10122014-Satish to check on this with some mainframe SME
|  | wCBS-Sample Message/File | N/A | 2014-12-09 | 2014-12-09 | No | Isabel Taggart |  | Can proceed with a open Risk of rework during testing phase | 09122014-Sample file shared but not in a correct encoding 10122014-Satish to check on this with some mainframe SME
| CHAPS | wCBS CHAPS-Interface Spec | 1.2 | 20/01/2015 27/02/2015 | 21/01/2015 02/03/2015 | No | BA(Deshdeep) |  | Few comments are addressed. Need to close other comments and move the document in Baseline folder. Need to know the Physical format of the message without this development can not progress. | 05012015-Nothing is shared with ADM team yet 20012015-Deshdeep has shared the Draft version of the document 21012015-ACH ADM review completed 03032015-Had a discussion with Deshdeep and clarified on the review comments
|  | wCBS CHAPS-Mapping Document | 1.2 | 20/01/2015 27/02/2015 | 21/01/2015 02/03/2015 | No | BA(Deshdeep) |  | Few comments are addressed. Need to close other comments and move the document in Baseline folder Need to know the Physical format of the message without this development can not progress. | 05012015-Nothing is shared with ADM team yet 20012015-Deshdeep has shared the Draft version of the document 21012015-ACH ADM review completed 03032015-Had a discussion with Deshdeep and clarified on the review comments
|  | wCBS CHAPS-Schema/Copy Book | N/A | N/A | N/A | N/A | N/A |  | Can proceed with a open Risk of rework during testing phase | 05012015-Nothing is shared with ADM team yet
|  | wCBS CHAPS-Sample Messages | N/A | N/A | N/A | N/A | N/A |  | Can proceed with a open Risk of rework during testing phase | 05012015-Nothing is shared with ADM team yet
TD01 | CHAPS | TD01-Interface Spec | Draft | 24/12/2014 18/02/2015 | 30/12/2014 TBD | No | BA(Deshdeep) |  | Few comments are addressed. Need to close other comments and move the document in Baseline folder | 09122014-Draft version shared with Nichola 24122014-Draft version shared with ADM team 30122014-Review comments shared with Deshdeep from ADM 16022015-Draft version of the document shared by Deshdeep
|  | TD01-Mapping Document | Draft | 24/12/2014 18/02/2015 | 30/12/2014 TBD | No | BA(Deshdeep) |  | Few comments are addressed. Need to close other comments and move the document in Baseline folder | 09122014-No details shared by BA 24122014-Draft version shared with ADM team 30122014-Review comments shared with Deshdeep from ADM 16022015-Draft version of the document shared by Deshdeep
|  | TD01-Schema/Copy Book | None | None | N/A | None | Nichola Mattock |  |  | 09122014-Dropped an email asking to provide the details
|  | TD01-Sample Message/File | None | None | N/A | None | Nichola Mattock |  | ACH ADM team checking with Nichola to get a sample message from the Queue | 09122014-Dropped an email for sample messages 16012015-Discussion happened with Nichola, she mentioned that on Monday she will check with switch team and try to get a sample message from queue. 21012015-Reminder email is sent to Nichola for the sample file
TD01 | International | None | N/A | N/A | N/A | N/A | N/A |  | Need to check with Deshdeep on this | None
NCA | CHAPS & International | NCA-Interface Spec | 1.1 | 01/12/2014 10/12/2014 12/12/2014 | 02/12/2014 12/12/2014 | Yes | BA(Deshdeep) |  | ACH ADM team to proceed on the development | 10122014-Deshdeep to cross check on the ADM comments and update back 10122014-Deshdeep Provided responses for the ADM comments 12122014-Deshdeep to cross check on ADM Comments 12122014-Deshdeep responded and updated the document. Still 2 items are open which he has to update. 21012015-Deshdeep has addressed the review comments and shared the updated document in BASELINE2 folder
|  | NCA-Mapping Document | 1.1 | 01/12/2014 10/12/2014 12/12/2014 | 02/12/2014 12/12/2014 | Yes | BA(Deshdeep) |  | ACH ADM team to proceed on the development | 10122014-Deshdeep to cross check on the ADM comments and update back 10122014-Deshdeep Provided responses for the ADM comments 12122014-Deshdeep to cross check on ADM Comments 12122014-Deshdeep responded and updated the document. Still 2 items are open which he has to update. 14012015-Deshdeep addressed few of the review comments. Yet to close other items. 21012015-Deshdeep has addressed the review comments and shared the updated document in BASELINE2 folder
|  | NCA-Schema/Copy Book | N/A | 2014-12-09 | 2014-12-09 | No | Isabel Taggart |  |  | 10122014-Satish to check on this with some mainframe SME 11122014-Discussed with Isabel and modified the copy books and generate the structure successfully 12122014-ACH ADM team to cross check if the Copy book structure and Interface Doc matches or not
|  | NCA-Sample Message/File | N/A | 2014-12-09 | 2014-12-09 | No | Isabel Taggart |  |  | 10122014-Satish to check on this with some mainframe SME 11122014-Risk is raised on the sample message indicating rework might be required during SIT
TMH - Batch | Not Applicable | Batch-Interface Spec | 1.0 | 2014-11-11 | 2014-12-09 | Yes | BA-Deshdeep |  | None | 10122014-Deshdeep to check on latest changes needs to be updated in RRC as per updated schema
|  | Batch-Mapping Document | N/A | 2015-02-05 | 2015-02-05 | Yes | BA-Deshdeep |  | Update with latest schema | 10122014-Deshdeep to confirm on this to ACH ADM team 05022015-Updated schemas are shared by ACH ADM team
|  | Batch-Schema | 1.3 | 09/12/2014 04/02/2015 | 2015-02-04 | Yes | ADM-Satish S M |  | None | 09122014-Draft version shared by Sumeet, Satish to review 05022015-Updated schemas are shared by ACH ADM team
|  | Batch-Sample Messages | 1.3 | 09/12/2014 04/02/2015 | 2015-02-04 | Yes | ADM-Satish S M |  | None | 09122014-Latest sample files are shared by ACH ADM team 05022015-Updated schemas are shared by ACH ADM team
Other Items | Not applicable | TD01 | N/A | N/A | N/A | N/A | TBD |  | Need to know if TD01 application capable of handling MQRFH2 header or not. If this is not achievable then design has to be changed to correlate request an response messages.

## DailyStatusTracker
| Task | Dependency
10/12/2014 (Wednesday)
Aneez | 1. WMQ Receiver flow 2. Validation issue 3. Promote the ESQL Module
Bhavan | 1. GPP and toolkit setup 2. EAD clarification 3. IF request Mapping started
Christo | 1. Reusing the TRC table 2. Map router - Wednesday
Jamie | 1. Assign some mapping flow | 1. Satish/Krishna to identify task
Krishna | 1. Coordinate with the team
Lakshmi | 1. KT started
Priya | 1. MsgSet wCBS, NCA 2. CHAPS and Internation for NCA 3. Creating msg definition based on the TDS
Sai Pranesh | 1. Policy table table 2. Interface handler 3. AIS Complex element Model Id 4. AIS IFW Interface handler
Sami
Satish | 1. Batch Processing 2. House keeping flow
Sumeet | 1. Exception flow testing in dev
Vijesh | 1. Modelling and Control message 2. Model table and updating TCM 3. Next Friday
Vinoth | N/A
11/12/2014 (Thursday)
Aneez | 1. WMQ Handler testing 2. Getting the clearcase client - Satish to cross check and update
Bhavan | 1. Sample message 2. Clear details on the structure 3. Need to finalise on the approach
Christo
Jamie
Krishna
Lakshmi
Priya | 1. No of occurences in wCBS
Sai Pranesh
Sami
Satish | 1. Update Batch sample messages
Sumeet
Vijesh
Vinoth
12/12/2014 (Friday)
Aneez | 1. WMQ Sender : InProgress 2. WMQ Receiver : Completed 3. HTTP Handler : Need to start
Bhavan
Christo | 1. Map Router
Jamie | 1. Assign some mapping flow
Krishna
Lakshmi | 1. KT started 2. Copy Book
Priya | 1. NCA Interface Review - Monday 2. SIT Defect
Sai Pranesh | 1. Incorporate review comments for HK-15/12/2014 2. IFW AIS Interface handler 3. Audit handler
Sami
Satish | 1. Batch Processing setup a call 2. Review completed for HK 3. Review completed for Batch Schema 4. Review of NCA on BA comments 5. Work on the design completion
Sumeet | 1. Working on the Batch schema updation 2. Start working on the Batch flow 3. TDS Message set 4. Exception handling
Vijesh
Vinoth
15/12/2014 (Monday)
Aneez | 1. WMQ Sender : InProgress 2. WMQ Receiver : Completed 3. HTTP Handler : Need to start 4. Already checked the existing flows
Bhavan | 1. Message set
Christo | 1. Map router : Need updates from the design discussion 2. Batch Processing start
Jamie
Krishna
Lakshmi | 1. Copy Books created message sets 2. Complete one message set comparison
Priya | 1. wCBS Interface and mapping review start
Sai Pranesh | 1. Incorporate review comments for HK, message set 2. IFW AIS Interface handler updates required from Satish & Krishna 3. Audit Handler : Completed
Sami | 1. WMQ Handler : Review completion by EOD today
Satish | 1. Batch Processing flow complete with table details 2. Design for the State Model implementation
Sumeet | 1. Batch processing developmet start 2. Batch schema completed
Vijesh
Vinoth
16/12/2014 (Tuesday)
Aneez | 1. WMQ Sender & Receiver : Incorporate review comments of Sami 2. Documentation for Handlers 3. HTTP Handler Details are
Bhavan | 1. MsgSet TDS 2. Check in Mqseries.net forum 3. Satish also to cross check 4. Sumeet and Vijesh also cross check
Christo | 1. Batch Control flow
Jamie
Krishna
Lakshmi | 1. Work on a new flow 2. Reusable function or Procedure
Priya | 1. wCBS Interface and mapping review start 2. Join NCA meeting
Sai Pranesh | 1. HK Review comments are completed 2. HK Message set 3. IFW AIS Interface handler : EOD 4. Audit handler : Send it for review
Sami
Satish | 1. Batch details share the details with Sumeet 2. Update the design 3. Reminder for the NCA Comments
Sumeet | 1. Batch request flow 2. Batch response flow
Vijesh
Vinoth
17/12/2014 (Wednesday)
Aneez | 1. WMQ Sender & Receiver 2. HTTP Handler 3. Documentaion completion
Bhavan | 1. Alter the AMD Interface Handler
Christo | 1. Map router completion 2. Additional Account Information 3. Batch control flow
Jamie | 1. Checking on the Database related flow
Krishna
Lakshmi | 1. Work on a new flow 2. Reusable function to generate Ach transaction id
Priya | 1. Check on the next task 2. Need to identify task 3. Complete excetion handler and send for review
Sai Pranesh | 1. HK Review comments are completed : Send it for review 2. HK Message set : Stop on this at the moment 3. IFW AIS Interface handler : Complete and send for review 4. Audit handler : Sent for review to Sami
Sami | 1. Complete the review of Audit handler
Satish | 1. Batch details update 2. wCBS Comments to be checked 3. NCA need to cross check on the copy book differences 4. Batch schema updates and share it with 5. TDS Message set for IF
Sumeet
Vijesh
Vinoth
18/12/2014 (Thursday)
Aneez | 1. HTTP Handler Progressing 2. WMQ Sender and Receiver Completed : Send it to Satish for review 3. Documentation completion
Bhavan | 1. AMD Interface handler : Monday EOD
Christo | 1. AMD request for AAI 2. Issue with the system
Jamie | 1. BatchId
Krishna | 1. Batch Processing review
Lakshmi | 1. Issue with DB and working on the testing generateCommonId
Priya | 1. Check with Jamie directly on the Exception 2. Start on the Validation Subflow
Sai Pranesh | 1. Audit handler : Sent for review to Sami 2. HK Review comments are completed : Send it for review 3. IFW AIS Interface handler : JUnit test cases and send it for review
Sami | 1. Audit handler review 2. HK Review 3. IFW AIS Interface review
Satish | 1. Batch details update 2. Check on the wCBS comment with Deshdeep 3. NCA Copy Book differences 4. Batch schema completion 5. Batch RRC document review 6. TDS message set Check 7. Check on the reusable funtion 8. Structure for the Internal message 9. Review comments from Priya 10. Mismatch in the fields of CopyBook and Interface Spec from Lakshmi 11. Email from Srimanjunath. NCA and wCBS Exchange rate formats
Sumeet | 1. Batch Discussion to happen 2. RRC Access
Vijesh | 1. Request path for the flow control 2. Send flow control for review 3. Structure for the internal message
Vinoth
19/12/2014 (Friday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress, need to share for review 2. WMQ Sender and Receiver : Review completed 3. Documentation pending
Bhavan | 1. AMD Interface handler : Monday EOD
Christo | 1. AMD request for AAI Completed 2. Issue with the system : Still pending
Jamie | 1. BatchId
Krishna | 1. Batch Processing review
Lakshmi | Sick Leave
Priya | 1. Exception Handling for send for review 2. Start on the Validation Subflow
Sai Pranesh | 1. Audit handler : Sent for review to Sami and review in progress 2. HK Review comments are completed : Send it for review 3. IFW AIS Interface handler : JUnit test cases and send it for review
Sami | 1. Audit handler review 2. HK Review 3. IFW AIS Interface review
Satish | 1. Batch details update 2. Check on the wCBS comment with Deshdeep 3. NCA Copy Book differences 4. Batch schema completion 5. Batch RRC document review 6. TDS Message set check 7 Check on the reusable funtion : As part of review this will be handled 8. Structure for the Internal message : Use AMD response only
Sumeet | 1. Batch Discussion to happen 2. RRC Access
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth
22/12/2014 (Monday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Sent for review to Satish 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. Facing issue while testing
Christo
Jamie | 1. BatchId generation function - Completed
Krishna
Lakshmi | 1. Issue with DB 2. Working on the Group Controller flow
Priya | 1. Exception Handling for send for review 2. Start on the Validation Subflow
Sai Pranesh | 1. Started with APS Interface Handler 2. AIS Interface Hanlder - Yet to receive Review comments
Sami | 1. Audit handler review - Completed 2. HK Review - Completed 3. IFW AIS Interface review
Satish | 1. Batch details update 2. Check on the wCBS comment with Deshdeep 3. NCA Copy Book differences 4. Batch schema completion - Completed 5. Batch RRC document review 6. TDS Message set check - Completed 7 Check on the reusable funtion : As part of review this will be handled - Completed 8. Structure for the Internal message : Use AMD response only - Completed
Sumeet | 1. Batch Discussion to happen 2. RRC Access
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth | Annual Leave
23/12/2014 (Tuesday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Sent for review to Satish 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 4. Validation flow rework
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. Facing issue while testing.
Christo | Leave
Jamie | 1. Cron Job
Krishna | Leave
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller flow
Priya | 1. Exception Handling for send for review - Sumeet is checking 2. NCA and wCBS mapping flow
Sami | 1. IFW AIS Interface review
Satish | 1. Batch details update - VM Issue 2. Check on the wCBS comment with Deshdeep 3. NCA Copy Book differences 4. Batch schema completion - Completed 5. Batch RRC document review 6. TDS Message set check - Completed 7. Check on the reusable funtion : As part of review this will be handled - Completed 8. Structure for the Internal message : Use AMD response only - Completed 9. WMQ Handler
Sumeet | 1. Batch Discussion to happen
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth | Leave
24/12/2014 (Wednesday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Sent for review to Satish 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 4. Validation flow rework - Not started
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. Facing issue while testing.
Christo | Leave
Jamie | 1. Cron Job
Krishna | Leave
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller fan out flow
Priya | 1. Exception Handling for send for review - Sumeet is checking 2. wCBS Message set and test with manually created sample message 3. NCA sent for review
Sai Pranesh | 1. Started with APS Interface Handler 2. AIS Interface Hanlder - Yet to receive Review comments
Sami | 1. IFW AIS Interface handler
Satish | 1. Update Aneez on what changes required in the Validation Subflow 2. Review WMQ Handler flows 3. AMD Interface handler cross check and add it in the plan - Completed
Sumeet | 1. Batch Flow progressing and supose to complete by 29th
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth | Leave
29/12/2014 (Monday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Sent for review to Satish 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 4. Validation flow rework - Not started
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. Facing issue while testing. - InProgress 2. Imported TD01 and need to check on it
Christo | Not keeping well
Jamie | 1. Cron Job
Krishna | 1. Discuss on the pending items
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller fan out flow - On Leave
Priya | 1. Exception Handling for send for review - Sumeet is checking 2. wCBS Message set and test with manually created sample message 3. NCA sent for review - On Leave
Sai Pranesh | 1. Started with APS Interface Handler 2. AIS Interface Hanlder - Yet to receive Review comments 3. Batch response flow
Sami | 1. IFW AIS Interface handler - InProgress 2. WCBS Mapping - InProgress 3. Flow controller - InProgress
Satish | 1. Update Aneez on what changes required in the Validation Subflow 2. Review WMQ Handler flows - InProgress 3. AMD Interface handler cross check and add it in the plan - Completed 4. Update on the plan with Krishna 5. Batch processing 6. ST Testing Test plan
Sumeet | 1. Batch Flow progressing and supose to complete by 29th
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth | Leave
30/12/2014 (Tuesday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Incorporate the review comments from Satish 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. Facing issue while testing. - InProgress 2. Imported TD01 and need to check on it 3. Trailer for IF is checked? Mapping is clear?
Christo | Not keeping well
Jamie | 1. Cron Job
Krishna | 1. Discuss on the pending items
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller fan out flow - On Leave
Priya | 1. Exception Handling for send for review - Sumeet is checking 2. wCBS Message set and test with manually created sample message 3. NCA sent for review - On Leave
Sai Pranesh | 1. Started with APS Interface Handler 2. AIS Interface Hanlder - Incorporate review commments 3. Batch response flow 4. Validation flow rework - Not started
Sami | 1. IFW AIS Interface handler - Completed 2. WCBS Mapping - InProgress 3. Flow controller - InProgress
Satish | 1. Update Aneez on what changes required in the Validation Subflow 2. Review WMQ Handler flows - Completed 3. AMD Interface handler cross check and add it in the plan - Completed 4. Update on the plan with Krishna 5. Batch processing - Completed 6. ST Testing Test plan
Sumeet | 1. Batch Flow progressing and supose to complete by 29th
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message
Vinoth | Leave
05/01/2015 (Monday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Shared for review with Satish 2. WMQ Sender and Receiver : Send flow testing 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 4. Take up one of the mapping flow
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - InProgress 2. IF Message Set - Completed 3. Trailer for IF is checked? Mapping is clear?
Christo | Not keeping well
Jamie | 1. Cron Job
Krishna | 1. Discuss on the pending items
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller fan out flow - On Leave
Priya | 1. Exception Handler - First round of review completed 2. NCA and wCBS Incorporated review comments from Sumeet - Completed 2. wCBS & NCA - Change as per the TDS format Message
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Incorporate review commments 3. Batch response flow - Completed
Sami | 1. IFW AIS Interface handler - Completed 2. WCBS Mapping - InProgress 3. Flow controller - InProgress
Satish | 1. Update Lakshmi on what changes required in the Validation Subflow - Completed 2. Review WMQ Handler flows - Completed 3. AMD Interface handler cross check and add it in the plan - Completed 4. Update on the plan with Krishna - InProgress 5. Batch processing - Completed 6. ST Testing Test plan - Share it with the team 7. Cron Job Function - Discuss with Jamie 8. Check on the Multiple acctNo validation subflow
Sumeet | 1. Batch Flow progressing and supose to complete by 29th
Vijesh | 1. Request path for the flow control 2. Sent flow control for review 3. Structure for the internal message On Leave
Vinoth | Leave
06/01/2015 (Tuesday)
Aneez | 1. HTTP Handler Progressing : Unit testing, Link test in progress - Satish has to review the code - 09/01/2015 2. WMQ Sender and Receiver : Completed 3. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 4. Take up one of the mapping flow 5. Start with Aggregation flow - Need to get updates from Krishna
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - InProgress 2. IF Message Set - Completed 3. IF Mapping flow - Trailer part mapping 4. Trailer for IF is checked? Mapping is clear?
Christo | Not keeping well
Jamie | 1. Cron Job - Further discussion needs to happen with Sarit/Vinoth and Satish
Krishna | 1. Aggregation flow
Lakshmi | 1. Issue with DB, call Help desk 2. Working on the Group Controller fan out flow - On Leave 3. wCBS Message set - Completed 4. wCBS Mapping - InProgress
Priya | 1. Exception Handler - First Roud of review completed 2. NCA Message set - Completed 3. NCA Mapping - InProgress 50% 4. wCBS & NCA - Change as per the TDS format Message
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Incorporate review commments 3. Batch response flow - Completed
Satish | 1. Update Lakshmi on what changes required in the Validation Subflow - Completed 2. Review WMQ Handler flows - Completed 3. AMD Interface handler cross check and add it in the plan - Completed 4. Update on the plan with Krishna - InProgress 5. Batch processing - Completed 6. ST Testing Test plan - Share it with the team 7. Cron Job Function - Discuss with Jamie 8. Check on the Multiple acctNo validation subflow 9. Started with APS Interface Handler
Sumeet | 1. Batch Flow progressing and supose to complete by 29th
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Cross check on comments 3. Structure for the internal message On Leave
Vinoth | Leave
09/01/2015 (Friday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - Satish has to review the code - 09/01/2015 2.. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Need to get updates from Krishna - 14-Jan 4. Start configuring the Link testing for APS
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Testing and Review 2. IF Message Set - Completed 3. IF Mapping flow - Trailer part mapping 4. Trailer for IF is checked? Mapping is clear?
Christo | Not keeping well
Jamie | 1. Need to check on any new task
Krishna | 1. Aggregation flow
Lakshmi | 1. Issue with DB, call Help desk. Rebuild the VM. 2. Working on the Group Controller fan out flow - AIS is working fine. 3. wCBS Message set - Completed 4. wCBS Mapping - InProgress, add the mapping dounts in the Review sheet
Priya | 1. Exception Handler - Satish to close the comments 2. NCA Message set - Completed 3. NCA Mapping - InProgress 50% 4. Stand In flow check existing flow
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Incorporate review commments 3. Batch Control Request flow - InProgress
Satish | 1. Update Lakshmi on what changes required in the Validation Subflow - Completed 2. Review WMQ Handler flows - Completed 3. AMD Interface handler cross check and add it in the plan - Completed 4. Update on the plan with Krishna - InProgress 5. Batch processing - Completed 6. ST Testing Test plan - Share it with the team 7. Cron Job Function - Discuss with Jamie 8. Check on the Multiple acctNo validation subflow 9. Started with APS Interface Handler 10. Ask Deshdeep to add about EOD in the IF Mapping sheet
Sumeet | 1. Batch Flow progressing and supose to complete by 29th 2. EOD send the Batch flows for review to Satish
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Satish to Review the code
Vinoth | None
12/01/2015 (Monday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - Satish has to review the code - 09/01/2015 2.. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish 4. Start configuring the Link testing for APS - InProgress
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Vijesh to update 2. IF Mapping flow - Trailer completed. Header and Body review comments to be udpated from DD
Christo | 1. MapRouter - Share for review 2. AMD APS - Mapping to be started 3. AIS Core response handler - InProgress 4. rCBS Interface Handler - Kaushik to cross check
Jamie | 1. TD01 Message set
Krishna | 1. Aggregation flow 2. Review AMD AAI Mapping flow
Lakshmi | 1. Issue with DB, call Help desk. - Closed 2. Working on the Group Controller fan out flow - AIS is working fine. 3. wCBS Mapping - InProgress, add the mapping doubts in the Review sheet
Priya | 1. Exception Handler - Completed 2. NCA Mapping - InProgress 50% 3. Stand In flow check existing flow - InProgress
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Incorporate review commments 3. Batch Control Request flow - Sumeet to update on it
Satish | 1. Update Lakshmi on what changes required in the Validation Subflow - Completed 2. Batch processing - Update the schema to include the TD01 Troux Id 3. ST Testing Test plan - Share it with the team 4. Started with APS Interface Handler - InProgress 5. HTTP Handler Review - Review 1 Partially Completed 6. AIS Interface Hanlder - Review 2 7. Map Router Review - Completed first round 8. Audit Handler - Review 4
Sumeet | 1. Batch Flow progressing and supose to complete by 29th 2. EOD send the Batch flows for review to Satish Training
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Satish to Review the code 3. End to end testing for AIS
Vinoth | Leave
13/01/2015 (Tuesday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - InProgress 2. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish 4. Start configuring the Link testing for APS - InProgress
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Vijesh to update 2. IF Mapping flow - Trailer completed. Header and Body review comments to be udpated from DD 3. Delete namespace - Recursive function End by 13-01-15
Christo | 1. MapRouter - Share for review 2. AMD APS - Mapping to be started 3. AIS Core response handler - InProgress 4. rCBS Interface Handler - Request handler is completed
Jamie | 1. TD01 Message set - InProgress
Krishna | 1. Aggregation flow - InProgress 2. Review AMD AAI Mapping flow - InProgress
Lakshmi | 1. Issue with DB, call Help desk. - Closed 2. Working on the Group Controller fan out flow - AIS is working fine. 3. wCBS Mapping - InProgress, add the mapping doubts in the Review sheet 4. Emulator - Cross check AMD AAI
Priya | 1. Exception Handler - Completed 2. NCA Mapping - InProgress 50%, need updates from 3. Stand In flow check existing flow - InProgress 4. Emulator - Cross check Batch TMH
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Incorporate review commments 3. Batch Control Request flow - Sumeet to update on it 4. Emulator - Cross check on the GetNPA Message structure
Satish | 1. Batch processing - Update the schema to include the TD01 Troux Id - Completed 2. ST Testing Test plan - Share it with the team 3. Started with APS Interface Handler - InProgress 4. HTTP Handler Review - Completed 5. AIS Interface Hanlder - Sai to share updated code 6. Map Router - Further discuss required 8. Audit Handler - Pending 9. Update to Deshdeep on the mapping comments 10. Review Housekeeping flow and SP 11. Check on the Exception handling monitoring activities 12. Recovery Handler and Leader Election progress
Sumeet | 1. Batch Flow progressing and supose to complete by 29th 2. EOD send the Batch flows for review to Satish Training
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Satish to Review the code 3. End to end testing for AIS
Vinoth | Leave
14/01/2015 (Wednesday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - InProgress 2. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish 4. Start configuring the Link testing for APS - InProgress
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Vijesh to update 2. IF Mapping flow - Trailer completed. Header and Body review comments to be udpated from DD - 16/01/15 3. Delete namespace - Recursive function End by 13-01-15 - Testing
Christo | 1. MapRouter - Testing InProgress 2. AMD AAI - Share it with Satish 3. Review Stand-In flow
Jamie | 1. TD01 Message set - PC and LAN Header completed
Kaushik | 1. AMD APS - Mapping to be started - 14/01/15
Krishna | 1. Aggregation flow - InProgress 2. Review AMD AAI Mapping flow - Completed
Lakshmi | 1. Working on the Group Controller fan out flow - AIS is working fine. - 20/01/15 2. wCBS Mapping - InProgress, add the mapping doubts in the Review sheet 3. Emulator - Cross check AMD AAI - Started on 13/01/15
Priya | 1. NCA Mapping - InProgress 50%, need updates from 2. Stand In flow check existing flow - Christo to review 3. Emulator - Cross check Batch TMH
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Vijesh to review 3. Batch Control Request flow - Sumeet to update on it 4. Emulator - Cross check on the GetNPA Message structure
Satish | 1. ST Testing Test plan - Share it with the team 2. Started with APS Interface Handler - InProgress 3. AIS Interface Hanlder - Sai to share updated code 4. Map Router - Further discuss required 5. Audit Handler - Review Pending 6. Update to Deshdeep on the mapping comments 7. Review Housekeeping flow and SP 8. Check on the Exception handling monitoring activities 9. Recovery Handler and Leader Election progress
Sumeet | 1. Batch Flow progressing and supose to complete by 29th 2. EOD send the Batch flows for review to Satish Training
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | Leave
16/01/2015 (Friday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - InProgress 2. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish (can be started - VM issues) 4. Start configuring the Link testing for APS - InProgress (because of VM issues)
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Vijesh will take it up. 2. IF Mapping flow - Trailer completed. Header and Body review comments to be udpated from DD - 16/01/15 -- Thorough review for every mapping field is required. 3. Delete namespace - Recursive function End by 13-01-15 -- Sent for review to Satish.
Christo | 1. MapRouter - Testing InProgress -- Done. 2. AMD AAI - Share it with Satish -- In progress (ETA Mon EOD) 3. Review Stand-In flow -- Pending AMD request mapping done
Jamie | 1. TD01 Message set - PC and LAN Header completed -- Waiting for TD01 response
Kaushik | 1. AMD APS(NPA response) - Mapping to be started - 14/01/15 -- started on 16th Jan
Krishna | 1. Aggregation flow - InProgress 2. Review AMD AAI Mapping flow - Completed
Lakshmi | 1. Working on the Group Controller fan out flow - AIS is working fine. - 20/01/15 2. wCBS Mapping - InProgress, add the mapping doubts in the Review sheet -- In progress 3. Emulator - Cross check AMD AAI - Started on 13/01/15 -- Completed but not yet tested. NO task assigned for now.
Priya | 1. NCA Mapping - InProgress 50%, need updates from 2. Stand In flow check existing flow - Christo to review 3. Emulator - Cross check Batch TMH -- Inputs from Sumeet for Batch message structure. 4. Testing for Exception handling scenarios.
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Vijesh to review 3. Batch Control Request flow --> Most of it is done. Sumeet will take it further. 4. Emulator - Cross check on the GetNPA Message structure
Satish | 1. ST Testing Test plan - Share it with the team --> in progress due to changing design 2. Started with APS Interface Handler - InProgress 3. AIS Interface Hanlder - Sai to share updated code 4. Map Router - Further discuss required 5. Audit Handler - Review Pending 6. Update to Deshdeep on the mapping comments --> still open 7. Review Housekeeping flow and SP --> Not yet started 8. Check on the Exception handling monitoring activities -- Will be taken up later on. 9. Recovery Handler and Leader Election progress -- Will be taken up later on. 10. Review the namespace deletion function -- Yet to start 11. Checking with Vinod on standin and update Priya
Sumeet | 1. Batch Flow progressing and supose to complete by 29th -- Draft structure for Batch flows has been shared with Satish. Still lot of modifications need to be done. Working on it. 2. Exception handling scenarios --> Creating the spreadsheet for list of exceptions. In progress
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | Leave
19/01/2015 (Monday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - InProgress 2. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish (can be started - VM issues) 4. Start configuring the Link testing for APS - InProgress (because of VM issues)
Bhavan | 1. Working on AMD Interface handler and will be sharing the code for review EOD. - Vijesh will take it up. 2. IF Mapping flow - Trailer completed. Header and Body review comments to be udpated from DD - 16/01/15 -- Review for mapping is complete and mapping sheet has been updated 3. Delete namespace - Recursive function End by 13-01-15 -- Satish has reviewed, task completed.
Christo | 1. MapRouter - Testing InProgress -- Done. 2. AMD AAI - Share it with Satish -- Complete. 3. Review Stand-In flow -- Pending 4. rCBS and Common controller mapping -- Will be completed today 5. AMD request mapping - Complete
Jamie | 1. TD01 Message set - PC and LAN Header completed -- Waiting for TD01 response
Kaushik | 1. AMD APS(NPA response) - Mapping to be started - 14/01/15 -- Task completed on 19th Jan
Krishna | 1. Aggregation flow - InProgress 2. Review AMD AAI Mapping flow - Completed
Lakshmi | 1. Working on the Group Controller fan out flow - AIS is working fine. - 20/01/15 2. wCBS Mapping - InProgress, add the mapping doubts in the Review sheet -- Complete 3. Emulator - Cross check AMD AAI - Started on 13/01/15 -- Completed and tested as well.
Priya | 1. NCA Mapping - InProgress 50%, need updates from 2. Stand In flow check existing flow - Christo to review -- (StandIN flow doubts to be discussed) 3. Emulator - Cross check Batch TMH -- Message structure discussed with Sumeet 4. Testing for Exception handling scenarios. -- Will be finalized after call with James Potter
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Working on modifications in AIS interface handler 3. Batch Control Request flow --> Most of it is done. Sumeet will take it further. 4. Emulator - Cross check on the GetNPA Message structure
Satish | 1. ST Testing Test plan - Share it with the team --> Completed today. 2. Started with APS Interface Handler - InProgress 3. AIS Interface Hanlder - Sai to share updated code 4. Map Router - Further discuss required 5. Audit Handler - In progress and will be completed today. 6. Update to Deshdeep on the mapping comments --> still open 7. Review Housekeeping flow and SP --> Not yet started 8. Check on the Exception handling monitoring activities -- Will be taken up later on. 9. Recovery Handler and Leader Election progress -- Will be taken up later on. 10. Review the namespace deletion function -- Task completed. Comments provided to Bhavan. 11. Checking with Vinod on standin and update Priya
Sumeet | 1. Batch Flow progressing and supose to complete by 29th -- Draft structure for Batch flows has been shared, Some doubts to be discussed with Satish. ACK msg handling yet to be decided. Working on it. 2. Exception handling scenarios --> Have set up call with James Potter to discuss on the Tivoli configuration. 3. Inputs provided to Priya for creation of Batch Processing Emulator, will have a second round of discussion if needed.
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | Leave
20/01/2015 (Tuesday)
Aneez | 1. HTTP Handler Progressing : Updated code to be sent to Satish - InProgress 2. Documentation on usage of the WMQ Handler and HTTP Handler - Pending 3. Start with Aggregation flow - Updates to be received from Krishna and Satish (can be started - VM issues) 4. Start configuring the Link testing for APS - InProgress (because of VM issues)
Bhavan | 1. Namespace deletion is complete -- No task for today.
Christo | 1. Review Stand-In flow -- Pending for inputs. 2. rCBS and Common controller mapping -- Completed . Working on response path for the same.
Jamie | 1. TD01 Message set - PC and LAN Header completed -- Waiting for TD01 response
Kaushik | 1. AMD APS(NPA response) - Mapping to be started - 14/01/15 -- Desktop allocation issue.
Krishna | 1. Aggregation flow - InProgress (inputs to be provided to Aneez)
Lakshmi | 1. wCBS Mapping - Message set creation -- Completed today. No further task assigned. 2. Emulator - Cross check AMD AAI - Started on 13/01/15 -- Completed and tested as well.
Priya | 1. NCA Mapping - InProgress 50%, need updates. 2. Stand In flow check existing flow - Christo to review -- (StandIN flow doubts to be discussed) --> waiting for confirmation from AMD 3. Emulator - Cross check Batch TMH -- Emulator completed with hard coded values. 4. Testing for Exception handling scenarios. -- Will be finalized after call with James Potter 5. Working on the message set change -- Started today(20th Jan)
Sai Pranesh | 1. Started with APS Interface Handler - Completed as per AIS 2. AIS Interface Hanlder - Working on modifications in AIS interface handler 3. Batch Control Request flow --> Most of it is done. Sumeet will take it further. 4. Emulator - Cross check on the GetNPA Message structure -- Not yet started, On sick leave today
Satish | 1. ST Testing Test plan - Share it with the team --> Completed today. 2. Started with APS Interface Handler - InProgress 3. AIS Interface Hanlder - Sai to share updated code 4. Map Router - Further discuss required 5. Audit Handler - Task Complete, Will be shared after this call. 6. Update to Deshdeep on the mapping comments --> still open 7. Review Housekeeping flow and SP --> Not yet started 8. Check on the Exception handling monitoring activities -- Will be taken up later on. 9. Recovery Handler and Leader Election progress -- Will be taken up later on. 10. Checking with Vinod on standin and update Priya
Sumeet | 1. Batch Flow -- Discussion with Satish about BatchRequest structure and one mapping query is done. 2. Exception handling scenarios --> Discussed with James. Will complete this by today EOD. 3. Inputs provided to Priya for creation of Batch Processing Emulator -- will have a second round of discussion if needed. 4. Discussion with Priya on the message set modification. -- In progress. 5. Namespace strip function -- Will check if the code can be shortened.
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | Leave
22/01/2015 (Thursday)
Aneez | 1. Start with Aggregation flow - Should be complete by Fri(23rd Jan) 2. Start configuring the Link testing for APS - [On hold] Will be taken up after Aggregation is done.
Bhavan | VM issue -- Broker not starting
Christo | 1. Review Stand-In flow -- Pending for inputs. 2. Awaiting design changes for AIS MK architecture.
Jamie | 1. TD01 Message set - PC and LAN Header completed -- Waiting for TD01 response
Kaushik | ON leave till 23rd Jan
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 1. AIS Link testing -- Task assigned by Vijesh. Delayed till design confirmation comes from Satish. 2. Mapping clarifications required even after Deshdeep's comments. Call at 6pm IST today.
Priya | 1. NCA Mapping - Mapping clarifications from DD have been gone through. Will discuss in tiday's call at 6pm IST. 2. Stand In flow check existing flow - Christo to review -- (StandIN flow doubts to be discussed) --> waiting for confirmation from AMD 3. Emulator - Cross check Batch TMH -- Emulator completed with hard coded values. 5. Working on the message set change -- In progress (Challenges faced, working on it)
Sai Pranesh | 1. AIS Interface Hanlder - Working on modifications in AIS interface handler 2. Working on Audit handler review comments -- Only one comment is left, Rest all implemented. 3. Emulator - Cross check on the GetNPA Message structure -- Not yet started 4. Working on APS interface handler -- In progress
Satish | 1. Started with APS Interface Handler - InProgress 2. AIS Interface Hanlder - Sai to share updated code 3. Audit Handler - Completed. 4. Update to Deshdeep on the mapping comments --> Done 5. Review Housekeeping flow and SP --> Not yet started 6. Check on the Exception handling monitoring activities -- Will be taken up later on. 7. Recovery Handler and Leader Election progress -- Will be taken up later on. 8. Checking with Vinod on standin and update Priya 9. wCBS SPA messgae format has been reviewed and comments updated. 10. Spoken to design team for Queue naming convention -- Changing underscore to dot. Awaiting reply. 11. Mapping queries call today. -- NCA and wCBS discussion
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set. 2. Exception handling scenarios --> Done. Creation of spreadsheet in progress 3. Inputs provided to Priya for creation of Batch Processing Emulator -- will have a second round of discussion if needed. For now, this task is done. 4. Discussion with Priya on the Mapping message set modification. -- Testing in progress. 5. Namespace strip function -- Will check if the code can be shortened. -- In progress 6. Aggregation flow implementation -- Approach decided. Aneez working on it. 7. Facing Juniper issues today -- Managing work on other people's VM
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | N.A
23/01/2015 (Friday)
Aneez | 1. Start with Aggregation flow - Should be complete by Fri(23rd Jan) 2. Start configuring the Link testing for APS - [On hold] Will be taken up after Aggregation is done. 3. On leave today.
Bhavan | VM issue -- Broker not starting
Christo | 1. Review Stand-In flow -- Pending for inputs. 2. Awaiting design changes for AIS MK architecture.
Jamie | 1. On leave today
Kaushik | On leave today
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 1. AIS Link testing -- Task assigned by Vijesh. Delayed till design confirmation comes from Satish. 2. Mapping clarifications for DD's comments. Call done. 7 queries still pending. No timelines
Priya | 1. NCA Mapping - Mapping clarifications from DD have been gone through. Will discuss in tiday's call at 6pm IST. -- Implementing changes. ETA: Tuesday EOD. 2. Stand In flow check existing flow - Christo to review -- (StandIN flow doubts to be discussed) --> waiting for confirmation from AMD 3. Emulator - Cross check Batch TMH -- Emulator completed with hard coded values. 5. Working on the message set change -- In progress (working on it)
Sai Pranesh | 1. AIS Interface Hanlder - Working on modifications in AIS interface handler . Test cases pending. 2. Working on Audit handler review comments -- Implemented. 3. Emulator - Cross check on the GetNPA Message structure -- Not yet started 4. Working on APS interface handler -- Complete. Test cases pending for AIS and APS interface handler.
Satish | 1. Started with APS Interface Handler - InProgress 2. AIS Interface Hanlder - Sai to share updated code 3. Audit Handler - Completed. 4. Update to Deshdeep on the mapping comments --> Done 5. Review Housekeeping flow and SP --> Not yet started 6. Check on the Exception handling monitoring activities -- Will be taken up later on. 7. Recovery Handler and Leader Election progress -- Will be taken up later on. 8. Checking with Vinod on standin and update Priya 9. wCBS SPA messgae format has been reviewed and comments updated. 10. Spoken to design team for Queue naming convention -- Changing underscore to dot. Awaiting reply. 11. Mapping queries call today. -- NCA and wCBS discussion
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Still workin on it. 2. Exception handling scenarios --> Complete. Mail sent to James Potter. 4. Discussion with Priya on the Mapping message set modification. -- Testing in progress. 5. Namespace strip function -- Will check if the code can be shortened. -- In progress 6. Aggregation flow implementation approach -- Finalized
Vijesh | 1. Request path for the flow control 2. Sent flow control for review - Send it for review - 16/01/15 3. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 4. rCBS Interface Handler - Share it fore review with Satish
Vinoth | N.A
27/01/2015 (Tuesday)
Aneez | 1. Start with Aggregation flow - Should be complete by Fri(23rd Jan) 2. Start configuring the Link testing for APS - [On hold] Will be taken up after Aggregation is done. 3. On leave today.
Bhavan | Awaiting IF mapping clarifications. Mapper flow has to be created.
Christo | 1. Review Stand-In flow -- Pending for inputs. 2. Awaiting design changes for AIS MK architecture.
Jamie | 1. On leave today
Kaushik | Desktop allocation issue.
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 1. AIS Link testing -- Task assigned by Vijesh. Delayed till design confirmation comes from Satish. 2. wCBS mapping is done -- Will be provided to Sumeet for review. -- On leave today
Priya | 1. NCA Mapping - Mapping clarifications from DD have been gone through. Will discuss in tiday's call at 6pm IST. -- Implementing changes. ETA: Tuesday EOD. 2. Stand In flow check existing flow - Christo to review -- (StandIN flow doubts to be discussed) --> waiting for confirmation from AMD 3. Emulator - Cross check Batch TMH -- Emulator completed with hard coded values. 5. Working on the message set change -- Done. Mapper flow has to be created.
Sai Pranesh | 1. AIS Interface Hanlder - Working on modifications in AIS interface handler . Test cases pending. 2. Emulator - Cross check on the GetNPA Message structure -- Not yet started 3. Test case framework creation --> In progress.
Satish | 1. Started with APS Interface Handler - InProgress 2. AIS Interface Hanlder - Sai to share updated code 3. Audit Handler - Will be closed today. 4. Review Housekeeping flow and SP --> Not yet started 5. Check on the Exception handling monitoring activities -- Will be taken up later on. 6. Recovery Handler and Leader Election progress -- Will be taken up later on. 7. Checking with Vinod on standin and update Priya 8. wCBS SPA messgae format has been reviewed and comments updated. 9. Spoken to design team for Queue naming convention -- Changing underscore to dot. Awaiting reply. 10. Mapping queries call today. -- NCA and wCBS discussion 11. TD01 orchestration will now be taken up by AMD team.
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Testing in progress. 2. Exception handling scenarios --> James has set up the alerting. Scenarios to be generated again. 4. Discussion with Priya on the Mapping message set modification. -- Complete. 5. Namespace strip function -- Complete. No change required
Vijesh | 1. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 2. Internal message structure review that is shared by Satish.
Vinoth | N.A
28/01/2015 (Wednesday)
Aneez | 1. Start with Aggregation flow - Should be complete by Fri(23rd Jan) 2. Start configuring the Link testing for APS - [On hold] Will be taken up after Aggregation is done.
Bhavan | 1. Working on mapper main flow --> that calls IF mapping subflow
Christo | 1. Design changes finalized --> Working on AMD response mapping
Jamie | Created TD-01 message set --> Kaushik to review
Kaushik | Desktop allocation issue.
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 2. wCBS mapping is done -- Will be provided to Sumeet for review. -- On leave today
Priya | 1. Stand In flow --> Sent to Satish for review. 2. Emulator - Batch TMH Emulator completed with hard coded values. 3. IF mapping code -- Mapping done. Review pending with Sumeet. 4. Wrapper component to be created
Sai Pranesh | 1. Emulator - Cross check on the GetNPA Message structure -- Not yet started 2. Test case framework creation --> In progress for APS interface handler
Satish | 1. Review Housekeeping flow and SP --> Not yet started 2. Recovery Handler and Leader Election progress -- Will be taken up later on. 3. Standin review -- Pending 4. wCBS SPA messgae format has been reviewed and comments updated. 5. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion 6. Updating Batch schema, table request form and values for table.
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Testing in progress. 2. Exception handling scenarios -->Exception scenarios to be generated again. 3. Review to be done for the following flows --> AIS & APS interface handler, IF, wCBS, NCA mapping components, rCBS handler, CS handler.
Vijesh | 1. End to end testing for AIS -- Same status will continue for this week, as Vijesh is doing end to end testing for complete AIS. 2. Internal message structure review that is shared by Satish.
Vinoth | N.A
29/01/2015 (Thursday)
Aneez | 1. Start with Aggregation flow - Complete. Pending for review with Sumeet. Review can be delayed because more set of requirements might come. 2. Start configuring the Link testing for APS - In progress
Bhavan | 1. Working on mapper main flow --> Complete.
Christo | 1. Design changes finalized --> Working on AMD response mapping -- Today EOD
Jamie | Created TD-01 message set --> Kaushik to review
Kaushik | Desktop allocation issue.
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 2. wCBS mapping is done -- Will be provided to Sumeet for review. -- On sick leave today
Priya | 1. Stand In flow --> Sent to Satish for review. 2. Emulator - Batch TMH Emulator completed with hard coded values. 3. IF mapping code -- Mapping done. Review pending with Sumeet. 4. Wrapper component to be created -- In progress ETA --> EOD today.
Sai Pranesh | 1. Emulator - Cross check on the GetNPA Message structure -- Not yet started 2. Test case framework creation --> APS handler is also complete. Pending for review with Sumeet.
Satish | 1. Review Housekeeping flow and SP --> Not yet started 2. Recovery Handler and Leader Election progress -- Discussion happened with Sarit. Code can be started on Monday. 3. Standin review -- Pending 4. wCBS SPA messgae format has been reviewed and comments updated. 5. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed. 6. Updating Batch schema -- Comlete 7. Table request form and values for table. -- In progress 8. Mapping from NPA to fan out control -- In progress
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Testing in progress. 2. Exception handling scenarios -->Exception scenarios to be generated again. 3. Review to be done for the following flows --> AIS & APS interface handler, IF, wCBS, NCA mapping components, rCBS handler, CS handler.
Vijesh | 1. Working on Fan out flow.
Vinoth | N.A
30/01/2015 (Friday)
Aneez | 1. Start with Aggregation flow - Complete. Pending for review with Sumeet. Review can be delayed because more set of requirements might come. 2. Start configuring the Link testing for APS - In progress
Bhavan | 1.On planned leave
Christo | 1. COMMON and rCBS request mapping --> In progress
Jamie | Created TD-01 message set --> Kaushik to review
Kaushik | Desktop allocation issue. --> Hopefully will be resolved by today.
Krishna | 1. Aggregation flow - Provided all the inputs
Lakshmi | 2. wCBS mapping is done -- Will be provided to Sumeet for review. -- On sick leave today
Priya | 1. Stand In flow --> Sent to Satish for review. 2. Wrapper component to be created -- In progress ETA --> EOD today.
Sai Pranesh | 1. Emulator - Cross check on the GetNPA Message structure -- Not yet started 2. Test case framework creation --> APS handler is also complete. Pending for review with Sumeet. 3. 3. Working on table creation task assigned by Vijesh -- ETA is EOD today
Satish | 1. Review Housekeeping flow and SP --> Not yet started 2. Recovery Handler and Leader Election progress -- Discussion happened with Sarit. Code can be started on Monday. 3. Standin review -- Pending 4. wCBS SPA messgae format has been reviewed and comments updated. 5. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed. 6. Updating Batch schema -- Comlete 7. Table request form and values for table. -- In progress 8. Mapping from NPA to fan out control -- In progress ON leave today
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Testing in progress. 2. Exception handling scenarios -->Exception scenarios to be generated again. 3. Review to be done for the following flows --> AIS & APS interface handler, IF, wCBS, NCA mapping components, rCBS handler, CS handler. --> Will be completed by 31st EOD. 4. Namespace function has been shortened considerably --> Task complete.
Vijesh | 1. Working on Fan out flow.
Vinoth | N.A
02/02/2015 (Monday)
Aneez | 1. Start with Aggregation flow - Complete. Pending for review with Sumeet. Review can be delayed because more set of requirements might come. 2. Configuring the Link testing for APS - In progress , will work on GetNPA emulator as well.
Bhavan | 1.On planned leave
Christo | 1. COMMON and rCBS request mapping --> Complete 2. rCBS response mapping --> In progress.
Jamie | Created TD-01 message set --> Kaushik to review
Kaushik | On leave today
Krishna | N.A
Lakshmi | 2. wCBS mapper main flow -- In progress
Priya | 1. Stand In flow --> Sent to Satish for review. 2. Wrapper component to be created -- Complete. Sent for review.
Sai Pranesh | 1. Emulator - Cross check on the GetNPA Message structure -- Aneez is working on this now! 2. Test case framework creation --> Review complete 3. Working on table creation task assigned by Vijesh -- Complete
Satish | 1. Review Housekeeping flow and SP --> Not yet started 2. Recovery Handler and Leader Election progress -- Discussion happened with Sarit. Code can be started on Monday. 3. Standin review -- Started. In progress 4. wCBS SPA messgae format has been reviewed and comments updated. 5. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed. 6. Updating Batch schema -- Comlete 7. Table request form and values for table. -- In progress 8. Mapping from NPA to fan out control -- In progress
Sumeet | 1. Batch Flow -- Creating wsdl and validating Batch msg set -- Should be complete by 2morrow. 2. Exception handling scenarios --> Done. Mail sent to James Potter. 3. Review to be done for the following flows --> AIS & APS interface handler, IF, wCBS, NCA mapping components, rCBS handler, CS handler. --> Will be completed by 31st EOD. --> This is complete. 4. Namespace function has been shortened considerably --> Task COMPLETE.
Vijesh | 1. Working on Fan out flow.
Vinoth | N.A
04/02/2015 (Wednesday)
Aneez | 1. Start with Aggregation flow - Complete according to set of requirements. 2. Configuring the Link testing for APS - In progress , will work on GetNPA emulator as well.
Bhavan | 1.Working on IF review comments -- ETA --> EOD today
Christo | 1. AIS Core response handler --> In progress. Will take time. Logic involved.
Jamie | Checking TD-01 sub flow
Kaushik | Leave
Krishna | 1. Table request form and values for table. -- In progress
Lakshmi | 2. wCBS mapper main flow -- In progress
Priya | 1. Stand In flow --> Sent to Satish for review. 2. Wrapper component to be created -- Incorporating review comments. 3. Modifying IF mset according to repeating bodies. -- Complete.
Sai Pranesh | 1. BNS interface handler -- In progress 2. APS rCBS mapping -- Completed.
Satish | 1. Review Housekeeping flow and SP --> Not yet started. 2. Recovery Handler and Leader Election progress -- Yet to be started. 3. Standin review -- Complete. Priya will work on review comments. 4. wCBS SPA messgae format has been reviewed and comments updated. --Shared with DD. Discussion required, TD-01 discussion will be done today. 5. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed. 6. Updating Batch schema -- Comlete 7. Mapping from NPA to fan out control -- In progress
Sumeet | 1. Batch Flow -- Integrating with mapping flows 2. Referring latest XSD's for Batch schema 3. StripNS PI sent to Satish -- Complete 4. MQ details--Queue list created.
Vijesh | 1. Working on Fan out flow.
05/02/2015 (Thursday)
Aneez | 1. Start with Aggregation flow - Complete according to set of requirements. 2. Configuring the Link testing for APS - In progress , will work on GetNPA emulator as well.
Bhavan | 1.Working on IF review comments -- Will be done by today. No task 2morrow onwards.
Christo | 1. AIS Core response handler --> In progress. Coding to be done by today, testing 2morrow
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | Will work on NPA response.
Krishna | 1. Table request form and values for table. -- Couple of days from today
Lakshmi | 2. GetNPAResponse structure -- In progress.
Priya | 1. Stand In flow --> Working on review comments
Sai Pranesh | 1. BNS interface handler -- Awaiting inputs from Vijesh and Christo 2. APS rCBS mapping -- Completed.
Satish | 1. Review Housekeeping flow and SP --> Not yet started. 2. Recovery Handler and Leader Election progress -- Discussion happened with Krishna. Yet to be started.. 3. wCBS SPA messgae format has been reviewed and comments updated. --Shared with DD. TD-01 is still not finalized. 4. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed. 5. Mapping from NPA to fan out control -- In progress--Kaushik will check on this.
Sumeet | 1. Batch Flow -- Integrating with mapping flows 2. Referring latest XSD's for Batch schema 3. Checking on the logic for FileName field in control message
Vijesh | 1. Working on Fan out flow.
AHM meet on 06/02/2015 Friday
09/02/2015 (Monday)
Aneez | 1. Configuring the Link testing for APS - In progress , will work on GetNPA emulator as well. 2. PS script for Routing config.
Bhavan | 1.Incorporate DB insert into TGD table.
Christo | 1. AIS Core response handler --> In progress. Coding to be done by today, testing 2morrow 2. BNS Request handler -- ETA today EOD.
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | Will work on NPA response.
Krishna | 1. Table request form and values for table. -- ETA: Couple of days from today
Lakshmi | 1. Incorporate DB insert into TGD table in wCBS mapping flow.
Priya | 1. Stand In flow --> Working on review comments
Sai Pranesh | 1. BNS interface handler -- Awaiting inputs from Vijesh.
Satish | 1. Review Housekeeping flow and SP --> Not yet started. 2. Recovery Handler and Leader Election progress -- Discussion happened with Krishna. Yet to be started.. 3. wCBS SPA messgae format has been reviewed and comments updated. --Shared with DD. TD-01 is still not finalized. 4. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed.
Sumeet | 1. Batch Flow -- Implementing changes acoording to Model and sequence ID. 2. NFT analysis-- File system getting crashed because of messages getting piled up. 3. Inserting records in TGD table -- from Mapping(NCA, IF, wCBS) components. 3. Working on FileName field logic.
Vijesh | 1. Working on Fan out flow.
10/02/2015 (Tuesday)
Aneez | 1.APS link testing --> In progress.
Bhavan | 1.Incorporate DB insert into TGD table.
Christo | 1. BNS Response handler -- In progress.
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | NPA response mapping to Fan-Out -- In progress.
Krishna | 1. Table request form and values for table. -- ETA: Couple of days from today
Lakshmi | 1. APS link testing along with Aneez.
Priya | 1. Stand In flow --> Working on StandIn flow.
Sai Pranesh | 1. Housekeeping flow review comments --> In progress.
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. wCBS SPA messgae format has been reviewed and comments updated. --Still pending. 3. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed.
Sumeet | 1. Batch Flow -- Incorporating TGD and TGC insert. (Model and Seq will be taken up later) 2. NFT package -- NFT package along with bulk auditing has been created and deployed. 3. Inserting records in TGD table -- from Mapping(NCA, IF, wCBS) components. 4. Working on FileName field logic -- Yet to start. 5. Working with Kaushik on the NPA response mapping component. -- In progress
Vijesh | 1. Complete AIS link testing
11/02/2015 (Wednesday)
Aneez | 1.APS link testing -- changing emulators --> In progress.
Bhavan | 1.Task yet to be decided.
Christo | 1. BNS Response handler -- In progress.
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | NPA response mapping to Fan-Out -- In progress.
Krishna | 1. Table request form and values for table. -- ETA: Couple of days from today
Lakshmi | 1. APS link testing along with Aneez.
Priya | 1. Stand In flow --> Working on StandIn flow.
Sai Pranesh | 1. Housekeeping flow review comments --> In progress.
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. wCBS SPA messgae format has been reviewed and comments updated. --Still pending. 3. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed.
Sumeet | 1. Batch Flow -- Incorporating TGD and TGC insert. (Model and Seq will be taken up later) 2. NFT package -- NFT package along with bulk auditing has been created and deployed. 3. Inserting records in TGD table -- from Mapping(NCA, IF, wCBS) components. 4. Working on FileName field logic -- Yet to start. 5. Working with Kaushik on the NPA response mapping component. -- In progress
Vijesh | 1. Complete AIS link testing
Sick leave on Friday
16/02/2015 (Monday)
Aneez | 1.Incorporating WMQ sender and reciever sub flows --> In progress.
Bhavan | 1.Task yet to be decided.
Christo | 1. APS E434 Request mapping -- In progress.
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | NPA response mapping to Fan-Out -- In progress.
Krishna | 1. Table request form and values for table. -- ETA: Couple of days from today
Lakshmi | 1. APS link testing -- Completed till NPA response.
Priya | 1. Stand In flow --> Complete.
Sai Pranesh | 1. Housekeeping flow review comments --> Complete.
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. wCBS SPA messgae format has been reviewed and comments updated. --Still pending. 3. Mapping queries discussion --> TD01, AMD NPA and wCBS CHAPS discussion -- not yet closed.
Sumeet | 1. Batch Flow -- Updating TGD and TGC insert.(Model and Seq will be taken up later) -- In progress 2. Working on FileName field logic -- Yet to start. 3. Working with Kaushik on the NPA response mapping component. -- In progress
Vijesh | 1. Complete AIS link testing
17/02/2015 (Tuesday)
Aneez | 1.Incorporating WMQ sender and reciever sub flows --> In progress.
Bhavan | 1.Collating message flow names for Resilience
Christo | 1. APS E434 Request mapping -- In progress (doubts discussed with Satish)
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | NPA response mapping to Fan-Out -- Done(few clarifications)
Krishna | 1. Table request form and values for table. Done
Lakshmi | 1. APS link testing -- Completed till NPA response.(changes in Interface handler)
Priya | 1. Complete AIS link testing(with test cases)
Sai Pranesh | 1. APS interface handler - few modifications implemented
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. Fan-In flow development -- In progress.
Sumeet | 1. Batch Flow -- Working on mset creation and OAT build 2. Working with Kaushik on the NPA response mapping component. -- Complete
Vijesh | 1. Complete AIS link testing
18/02/2015 (Wednesday)
Aneez | 1.Incorporating WMQ sender and reciever sub flows --> In progress.
Bhavan | 1.Collating message flow names for Resilience -- Complete
Christo | 1. APS E434 Request mapping -- In progress (doubts discussed with Satish)
Jamie | Checking TD-01 sub flow, change record creation
Kaushik | NPA response mapping to Fan-Out -- Done(few clarifications)
Krishna | 1. Table request form and values for table. Done
Lakshmi | 1. APS link testing -- Completed till NPA response.(changes in Interface handler)
Priya | 1. Complete AIS link testing(with test cases)
Sai Pranesh | 1. APS interface handler - few modifications implemented
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. Fan-In flow development -- In progress.
Sumeet | 1. Batch Flow -- Working on mset creation. 2.OAT deployment package: IPS, AIS and Exception --Complete.
Vijesh | 1. Complete AIS link testing -- 95% complete (incorporate latest AMD schema)
19/02/2015 (Thursday)
Aneez | 1.Incorporating WMQ sender and reciever sub flows --> In progress.
Bhavan | 1.Collating message flow names for Resilience -- Complete
Christo | 1. APS E434 Response mapping -- In progress
Jamie | Checking TD-01 sub flow, change record creation -- TD-01 mapping review
Kaushik | GCFI flow discussion with Sumeet -- In progress.
Krishna | 1. Table request form and values for table. Done
Lakshmi | 1. APS link testing -- Completed till NPA response.(changes in Interface handler)
Priya | 1. Complete AIS link testing(with test cases)
Sai Pranesh | 1. APS interface handler - few modifications implemented
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. Fan-In flow development -- In progress.
Sumeet | 1. Batch Flow -- Working on mset creation. 2. NFT pile up analysis -- In progress 3. GCFI discussion -- In progress.
Vijesh | 1. Complete AIS link testing -- 100% complete with 28 test case scenarios 2. Group Controller FanOut flow. -- In progress
20/02/2015 (Friday)
Aneez | 1.GCFO for APS along with Vijesh -- In progress
Bhavan | 1.Testing for the IF mapping flow
Christo | 1. APS E434 Response mapping -- In progress
Jamie | Prod Deployment
Kaushik | GCFI flow discussion with Sumeet -- In progress.
Krishna | 1. Table request form and values for table. Done
Lakshmi | 1. APS link testing -- Right now testing WCBS mapping flow.
Priya | 1. Complete AIS link testing(with test cases)
Sai Pranesh | 1. Bulk Audit research -- Issue found out (Query doesn't work on z/OS )
Satish | 1. Recovery Handler and Leader Election progress -- Yet to start. 2. Fan-In flow development -- Already shared with Offshore.
Sumeet | 1. Batch Flow -- Working on mset creation. 2. NFT pile up analysis -- In progress 3. GCFI discussion -- In progress.
Vijesh | 1. Complete AIS link testing -- 100% complete with 28 test case scenarios 2. APS Group Controller FanOut flow. -- In progress
03/04/2015 (Friday)
Aneez | Leave
Bhavan | 1.TD01-creation of emulator (In-progress)
Christo | Leave
Jamie
Kaushik | 1. TD01- Changes in NPAResponse subflow(done)
Krishna
Lakshmi | Leave
Priya | 1. WCBS Dev (In-progress)
Sai Pranesh | 1. Resilience ST Defect 642 & 645 (done)
Satish
Sumeet | 1. Batch Flow -- Changes to fit in MK
Vijesh | 1. Resilience ST Defect 642 & 645 (done) 2. TD01 - Fanout flow changes
20/04/2015 (Friday)
Aneez | 1. NFT local DEV testing 2. ST Defect # 701(In-Progress) 3. CR008 - Deployment
Bhavan | 1.TD01-verification of new changes (In-progress)
Christo | 1. CR008 - Deployment (Done)
Jamie | Leave
Kaushik | 1. NFT in local DEV 2. SIT Issues (In-progress)
Krishna
Lakshmi | Leave
Priya | 1. WCBS Dev (In-progress)
Sai Pranesh | 1. NFT local DEV testing
Satish
Sumeet | 1. Changes in Batch Flow 2. ST Defects
Vijesh | Leave